## Gravita Project WBS
WBS | Task Name | Duration (Days) | Predecessor | Resource Name | Type
1 | Project Initiation |  |  | Project Manager | Summary
1.1 | Initial Client Meeting | 1 |  | Project Manager | Task
1.2 | Understand Business Requirements | 2 | 1.1 | Business Analyst | Task
1.3 | Site Visit & Recycling Process Study | 1 | 1.2 | Project Manager | Task
1.4 | Define Project Scope | 1 | 1.3 | Project Manager | Task
1.5 | Project Kickoff Milestone | 0 | 1.4 | Project Sponsor | Milestone
2 | Project Planning |  |  |  | Summary
2.1 | Create Project Charter | 1 | 1.5 | Project Manager | Task
2.2 | Identify Stakeholders | 1 | 2.1 | Business Analyst | Task
2.3 | Develop WBS | 2 | 2.2 | Project Manager | Task
2.4 | Define Schedule | 1 | 2.3 | Scheduler | Task
2.5 | Resource Planning | 1 | 2.4 | HR Manager | Task
2.6 | Risk Identification | 1 | 2.5 | Risk Manager | Task
2.7 | Planning Completed Milestone | 0 | 2.6 | Project Manager | Milestone
3 | Process Analysis |  |  |  | Summary
3.1 | Analyze Scrap Collection Process | 2 | 2.7 | Business Analyst | Task
3.2 | Analyze Material Sorting Process | 2 | 3.1 | Process Engineer | Task
3.3 | Analyze Smelting Process | 2 | 3.2 | Process Engineer | Task
3.4 | Analyze Logistics Flow | 1 | 3.3 | Logistics Manager | Task
3.5 | Document Current Processes | 1 | 3.4 | Business Analyst | Task
3.6 | Process Analysis Milestone | 0 | 3.5 | Project Manager | Milestone
4 | System Design |  |  |  | Summary
4.1 | Define Data Requirements | 2 | 3.6 | Data Analyst | Task
4.2 | Design Reporting Structure | 2 | 4.1 | BI Developer | Task
4.3 | Design Dashboard Layout | 2 | 4.2 | BI Developer | Task
4.4 | Define KPIs for Recycling Efficiency | 2 | 4.3 | Business Analyst | Task
4.5 | Design Data Integration Plan | 1 | 4.4 | Data Engineer | Task
4.6 | System Design Approval | 1 | 4.5 | Project Sponsor | Task
4.7 | Design Completed Milestone | 0 | 4.6 | Project Manager | Milestone
5 | Development Phase |  |  |  | Summary
5.1 | Prepare Database Structure | 2 | 4.7 | Database Engineer | Task
5.2 | Develop Data Import Scripts | 2 | 5.1 | Data Engineer | Task
5.3 | Create ETL Processes | 3 | 5.2 | Data Engineer | Task
5.4 | Develop Power BI Data Model | 2 | 5.3 | BI Developer | Task
5.5 | Create Dashboards | 3 | 5.4 | BI Developer | Task
5.6 | Develop Reports for Management | 2 | 5.5 | BI Developer | Task
5.7 | Internal Testing | 1 | 5.6 | QA Engineer | Task
5.8 | Development Completed Milestone | 0 | 5.7 | Project Manager | Milestone
6 | Testing Phase |  |  |  | Summary
6.1 | Prepare Test Cases | 1 | 5.8 | QA Engineer | Task
6.2 | Unit Testing | 1 | 6.1 | QA Engineer | Task
6.3 | Integration Testing | 2 | 6.2 | QA Engineer | Task
6.4 | User Acceptance Testing | 1 | 6.3 | Client Team | Task
6.5 | Bug Fixing | 1 | 6.4 | Development Team | Task
6.6 | Testing Completed Milestone | 0 | 6.5 | Project Manager | Milestone
7 | Training & Deployment |  |  |  | Summary
7.1 | Prepare Training Material | 2 | 6.6 | Trainer | Task
7.2 | Conduct User Training | 1 | 7.1 | Trainer | Task
7.3 | Deploy System | 1 | 7.2 | IT Administrator | Task
7.4 | Project Go-Live Milestone | 0 | 7.3 | Project Sponsor | Milestone
8 | Project Closure |  |  |  | Summary
8.1 | Collect Feedback | 1 | 7.4 | Business Analyst | Task
8.2 | Prepare Final Documentation | 1 | 8.1 | Project Manager | Task
8.3 | Project Closure Milestone | 0 | 8.2 | Project Sponsor | Milestone