## Project Tracker
Project | Location | Planned Duration | Actual Duration | Delay Days | Material Status | Vendor | Cost | Risk
Project 001 | Bihar | 95 | 97 | -2 | Available | Apex | 31L | Low
Project 002 | Ladakh | 92 | 89 | 3 | Available | ABC | 95L | Low
Project 003 | Delhi | 67 | 52 | 15 | Delayed | RST | 93L | Medium
Project 004 | Bihar | 65 | 56 | 9 | Delayed | XYZ | 61L | Medium
Project 005 | Madhya Pradesh | 79 | 85 | -6 | Available | Apex | 76L | Medium
Project 006 | Gujarat | 79 | 84 | -5 | Shortage | Nexus | 64L | Critical
Project 007 | Chhattisgarh | 59 | 63 | -4 | Delayed | XYZ | 47L | Low
Project 008 | Bihar | 72 | 75 | -3 | Available | RST | 44L | Low
Project 009 | Ladakh | 93 | 81 | 12 | Shortage | RST | 66L | High
Project 010 | Punjab | 69 | 65 | 4 | Available | Sigma | 58L | Low
Project 011 | Himachal Pradesh | 59 | 60 | -1 | Partially Available | Sigma | 81L | Medium
Project 012 | Karnataka | 64 | 62 | 2 | Shortage | Sigma | 92L | Critical
Project 013 | Rajasthan | 80 | 78 | 2 | Delayed | XYZ | 24L | Medium
Project 014 | Himachal Pradesh | 95 | 97 | -2 | Available | Nexus | 66L | Low
Project 015 | Punjab | 88 | 89 | -1 | Partially Available | Apex | 32L | Medium
Project 016 | Maharashtra | 96 | 95 | 1 | Delayed | Apex | 51L | Medium
Project 017 | Gujarat | 87 | 58 | 29 | Shortage | Nexus | 82L | Medium
Project 018 | Telangana | 64 | 62 | 2 | Delayed | ABC | 85L | High
Project 019 | Uttar Pradesh | 75 | 72 | 3 | Partially Available | LMN | 57L | Low
Project 020 | Rajasthan | 70 | 53 | 17 | Available | Apex | 26L | Critical
Project 021 | Gujarat | 63 | 51 | 12 | Available | Sigma | 95L | Medium
Project 022 | Arunachal Pradesh | 89 | 74 | 15 | Available | Prime EPC | 65L | Medium
Project 023 | Karnataka | 83 | 81 | 2 | Available | LMN | 88L | Low
Project 024 | Arunachal Pradesh | 69 | 70 | -1 | Available | XYZ | 60L | Medium
Project 025 | Assam | 70 | 70 | 0 | Available | Nexus | 91L | Low
Project 026 | Uttarakhand | 70 | 60 | 10 | Available | VTL Infra | 73L | Medium
Project 027 | Chhattisgarh | 81 | 83 | -2 | Available | ABC | 30L | Low
Project 028 | Uttarakhand | 76 | 71 | 5 | Available | PQR | 75L | Low
Project 029 | Uttar Pradesh | 66 | 64 | 2 | Partially Available | XYZ | 88L | Medium
Project 030 | Uttarakhand | 96 | 67 | 29 | Available | PQR | 48L | High
Project 031 | Chhattisgarh | 86 | 89 | -3 | Available | ABC | 66L | Low
Project 032 | Rajasthan | 71 | 43 | 28 | Delayed | Prime EPC | 89L | High
Project 033 | Uttar Pradesh | 67 | 64 | 3 | Delayed | ABC | 58L | Medium
Project 034 | Maharashtra | 92 | 95 | -3 | Available | XYZ | 83L | Low
Project 035 | Karnataka | 59 | 45 | 14 | Partially Available | LMN | 90L | Medium
Project 036 | Punjab | 93 | 95 | -2 | Available | VTL Infra | 84L | Low
Project 037 | Jharkhand | 68 | 59 | 9 | Available | Prime EPC | 56L | Medium
Project 038 | Odisha | 59 | 61 | -2 | Available | PQR | 51L | Low
Project 039 | Telangana | 59 | 38 | 21 | Delayed | RST | 87L | High
Project 040 | Punjab | 96 | 82 | 14 | Partially Available | PQR | 31L | Medium
Project 041 | Jharkhand | 62 | 35 | 27 | Delayed | LMN | 95L | High
Project 042 | Uttarakhand | 68 | 60 | 8 | Delayed | XYZ | 24L | Medium
Project 043 | Himachal Pradesh | 72 | 78 | -6 | Delayed | PQR | 51L | High
Project 044 | Uttar Pradesh | 90 | 78 | 12 | Available | Apex | 37L | Medium
Project 045 | Odisha | 78 | 72 | 6 | Delayed | ABC | 64L | Medium
Project 046 | Rajasthan | 68 | 54 | 14 | Available | Nexus | 70L | High
Project 047 | Jharkhand | 70 | 42 | 28 | Partially Available | PQR | 21L | Medium
Project 048 | Uttar Pradesh | 81 | 66 | 15 | Partially Available | Sigma | 31L | Medium
Project 049 | Delhi | 85 | 88 | -3 | Partially Available | LMN | 47L | Medium
Project 050 | Arunachal Pradesh | 97 | 96 | 1 | Delayed | VTL Infra | 53L | Medium
Project 051 | Karnataka | 80 | 68 | 12 | Delayed | PQR | 51L | Medium
Project 052 | Arunachal Pradesh | 71 | 78 | -7 | Available | Nexus | 73L | Medium
Project 053 | Arunachal Pradesh | 62 | 63 | -1 | Available | ABC | 73L | Low
Project 054 | Jharkhand | 89 | 74 | 15 | Shortage | XYZ | 73L | High
Project 055 | Uttarakhand | 94 | 97 | -3 | Available | RST | 82L | Medium
Project 056 | Telangana | 75 | 74 | 1 | Delayed | PQR | 66L | Medium
Project 057 | Karnataka | 91 | 92 | -1 | Shortage | Sigma | 44L | High
Project 058 | Maharashtra | 93 | 82 | 11 | Delayed | Prime EPC | 83L | High
Project 059 | Haryana | 97 | 100 | -3 | Available | RST | 48L | Medium
Project 060 | Uttarakhand | 67 | 64 | 3 | Available | Prime EPC | 27L | Low
Project 061 | Delhi | 95 | 80 | 15 | Shortage | PQR | 49L | Critical
Project 062 | Uttar Pradesh | 61 | 54 | 7 | Available | Prime EPC | 84L | Low
Project 063 | Ladakh | 90 | 93 | -3 | Available | Apex | 77L | Low
Project 064 | Ladakh | 93 | 96 | -3 | Partially Available | Sigma | 82L | High
Project 065 | Arunachal Pradesh | 83 | 56 | 27 | Partially Available | RST | 49L | Critical
Project 066 | Jharkhand | 86 | 78 | 8 | Delayed | RST | 48L | High
Project 067 | Bihar | 75 | 58 | 17 | Available | LMN | 37L | High
Project 068 | Karnataka | 81 | 82 | -1 | Available | Sigma | 71L | Low
Project 069 | Chhattisgarh | 56 | 28 | 28 | Delayed | RST | 63L | Critical
Project 070 | Haryana | 81 | 66 | 15 | Delayed | Prime EPC | 46L | High
Project 071 | Himachal Pradesh | 72 | 69 | 3 | Delayed | PQR | 69L | High
Project 072 | Bihar | 63 | 39 | 24 | Available | ABC | 90L | High
Project 073 | Gujarat | 96 | 99 | -3 | Available | VTL Infra | 66L | Low
Project 074 | Bihar | 84 | 87 | -3 | Partially Available | RST | 71L | Medium
Project 075 | Delhi | 85 | 86 | -1 | Partially Available | ABC | 26L | Medium
Project 076 | Karnataka | 70 | 67 | 3 | Shortage | XYZ | 78L | High
Project 077 | Maharashtra | 68 | 67 | 1 | Shortage | XYZ | 95L | High
Project 078 | Gujarat | 74 | 71 | 3 | Partially Available | Sigma | 66L | High
Project 079 | Madhya Pradesh | 59 | 45 | 14 | Available | Nexus | 56L | High
Project 080 | Jharkhand | 91 | 82 | 9 | Delayed | Apex | 26L | High
Project 081 | Uttarakhand | 55 | 44 | 11 | Available | PQR | 76L | Low
Project 082 | Himachal Pradesh | 66 | 52 | 14 | Delayed | Prime EPC | 86L | High
Project 083 | Himachal Pradesh | 82 | 69 | 13 | Delayed | RST | 29L | Low
Project 084 | Jharkhand | 70 | 57 | 13 | Shortage | Prime EPC | 21L | High
Project 085 | Ladakh | 66 | 65 | 1 | Shortage | RST | 94L | High
Project 086 | Haryana | 55 | 48 | 7 | Available | Apex | 80L | High
Project 087 | Chhattisgarh | 85 | 74 | 11 | Delayed | LMN | 55L | Medium
Project 088 | Ladakh | 70 | 71 | -1 | Available | Sigma | 62L | Low
Project 089 | Jharkhand | 76 | 76 | 0 | Available | LMN | 33L | Low
Project 090 | Karnataka | 62 | 47 | 15 | Available | RST | 79L | Medium
Project 091 | West Bengal | 88 | 83 | 5 | Partially Available | PQR | 64L | Medium
Project 092 | Rajasthan | 55 | 49 | 6 | Delayed | RST | 88L | Low
Project 093 | Assam | 95 | 72 | 23 | Available | Prime EPC | 54L | High
Project 094 | Chhattisgarh | 83 | 80 | 3 | Delayed | XYZ | 32L | Low
Project 095 | Haryana | 86 | 87 | -1 | Available | XYZ | 56L | Medium
Project 096 | Chhattisgarh | 62 | 52 | 10 | Shortage | Apex | 46L | Critical
Project 097 | Telangana | 83 | 63 | 20 | Partially Available | Nexus | 57L | Medium
Project 098 | Bihar | 58 | 43 | 15 | Available | RST | 45L | High
Project 099 | Assam | 65 | 66 | -1 | Available | Nexus | 75L | Low
Project 100 | Haryana | 73 | 78 | -5 | Delayed | XYZ | 76L | High
Project 101 | Madhya Pradesh | 71 | 57 | 14 | Delayed | Sigma | 43L | High
Project 102 | Maharashtra | 89 | 87 | 2 | Partially Available | ABC | 27L | High
Project 103 | Chhattisgarh | 74 | 61 | 13 | Partially Available | RST | 77L | Medium
Project 104 | Telangana | 72 | 61 | 11 | Delayed | VTL Infra | 73L | High
Project 105 | Delhi | 71 | 75 | -4 | Partially Available | Nexus | 91L | High
Project 106 | Himachal Pradesh | 98 | 85 | 13 | Available | Apex | 78L | High
Project 107 | Odisha | 72 | 73 | -1 | Available | Prime EPC | 29L | Medium
Project 108 | West Bengal | 81 | 83 | -2 | Available | Prime EPC | 70L | Low
Project 109 | Punjab | 97 | 68 | 29 | Shortage | VTL Infra | 29L | High
Project 110 | Himachal Pradesh | 75 | 78 | -3 | Available | Apex | 18L | Low
Project 111 | Gujarat | 81 | 87 | -6 | Available | ABC | 74L | Low
Project 112 | Telangana | 72 | 64 | 8 | Delayed | ABC | 33L | High
Project 113 | Madhya Pradesh | 70 | 62 | 8 | Delayed | LMN | 29L | High
Project 114 | Punjab | 84 | 58 | 26 | Partially Available | Apex | 55L | Critical
Project 115 | Telangana | 81 | 70 | 11 | Available | LMN | 67L | High
Project 116 | Arunachal Pradesh | 87 | 81 | 6 | Partially Available | VTL Infra | 71L | Medium
Project 117 | Rajasthan | 72 | 64 | 8 | Shortage | Prime EPC | 92L | Medium
Project 118 | Jharkhand | 83 | 74 | 9 | Delayed | Prime EPC | 66L | High
Project 119 | Jharkhand | 67 | 48 | 19 | Delayed | ABC | 70L | High
Project 120 | Uttar Pradesh | 85 | 75 | 10 | Delayed | Prime EPC | 37L | High
Project 121 | Arunachal Pradesh | 63 | 50 | 13 | Delayed | XYZ | 74L | Medium
Project 122 | Assam | 84 | 87 | -3 | Available | XYZ | 37L | Low
Project 123 | Chhattisgarh | 71 | 73 | -2 | Available | Apex | 60L | Low
Project 124 | West Bengal | 75 | 64 | 11 | Partially Available | LMN | 26L | Medium
Project 125 | Maharashtra | 69 | 59 | 10 | Partially Available | Prime EPC | 30L | High
Project 126 | Uttarakhand | 74 | 58 | 16 | Delayed | VTL Infra | 63L | High
Project 127 | Bihar | 64 | 64 | 0 | Available | PQR | 39L | Medium
Project 128 | Haryana | 94 | 69 | 25 | Shortage | PQR | 92L | Critical
Project 129 | Ladakh | 84 | 73 | 11 | Delayed | RST | 77L | Medium
Project 130 | Himachal Pradesh | 65 | 71 | -6 | Partially Available | RST | 72L | Medium
Project 131 | Odisha | 74 | 74 | 0 | Partially Available | Nexus | 66L | Medium
Project 132 | Delhi | 91 | 93 | -2 | Available | RST | 68L | Medium
Project 133 | West Bengal | 91 | 63 | 28 | Shortage | Prime EPC | 95L | High
Project 134 | Madhya Pradesh | 69 | 60 | 9 | Available | PQR | 50L | Medium
Project 135 | Bihar | 95 | 87 | 8 | Shortage | PQR | 64L | High
Project 136 | Arunachal Pradesh | 73 | 73 | 0 | Available | VTL Infra | 87L | Low
Project 137 | Jharkhand | 87 | 58 | 29 | Available | RST | 79L | Medium
Project 138 | Odisha | 62 | 59 | 3 | Available | Apex | 68L | Medium
Project 139 | Karnataka | 60 | 56 | 4 | Delayed | RST | 65L | Medium
Project 140 | Ladakh | 79 | 70 | 9 | Available | Nexus | 21L | Medium
Project 141 | Uttarakhand | 75 | 56 | 19 | Shortage | RST | 77L | Critical
Project 142 | Ladakh | 62 | 59 | 3 | Delayed | LMN | 30L | Medium
Project 143 | Karnataka | 63 | 62 | 1 | Shortage | Sigma | 87L | Critical
Project 144 | Uttar Pradesh | 64 | 38 | 26 | Available | RST | 70L | Critical
Project 145 | Ladakh | 78 | 78 | 0 | Partially Available | VTL Infra | 30L | Low
Project 146 | Gujarat | 96 | 96 | 0 | Available | XYZ | 76L | Medium
Project 147 | Gujarat | 96 | 92 | 4 | Available | Nexus | 34L | Low
Project 148 | Rajasthan | 59 | 47 | 12 | Available | VTL Infra | 47L | Medium
Project 149 | Delhi | 93 | 96 | -3 | Partially Available | XYZ | 40L | Medium
Project 150 | Rajasthan | 63 | 67 | -4 | Available | ABC | 51L | Low
Project 151 | Karnataka | 81 | 66 | 15 | Available | Apex | 64L | Medium
Project 152 | Himachal Pradesh | 61 | 59 | 2 | Partially Available | RST | 84L | Medium
Project 153 | Assam | 96 | 80 | 16 | Partially Available | XYZ | 72L | Medium
Project 154 | Telangana | 83 | 85 | -2 | Available | RST | 34L | Low
Project 155 | Himachal Pradesh | 95 | 80 | 15 | Delayed | RST | 85L | Low
Project 156 | Uttarakhand | 87 | 82 | 5 | Shortage | LMN | 88L | High
Project 157 | Jharkhand | 83 | 61 | 22 | Delayed | XYZ | 71L | Critical
Project 158 | Bihar | 82 | 81 | 1 | Delayed | XYZ | 78L | Medium
Project 159 | Uttar Pradesh | 60 | 62 | -2 | Delayed | Apex | 34L | Medium
Project 160 | Uttar Pradesh | 92 | 68 | 24 | Delayed | Sigma | 63L | High
Project 161 | Haryana | 73 | 64 | 9 | Available | Prime EPC | 37L | Medium
Project 162 | Uttarakhand | 61 | 62 | -1 | Available | LMN | 91L | Medium
Project 163 | Telangana | 90 | 61 | 29 | Shortage | ABC | 89L | Critical
Project 164 | Odisha | 97 | 89 | 8 | Available | VTL Infra | 57L | Medium
Project 165 | Bihar | 55 | 53 | 2 | Delayed | ABC | 36L | Medium
Project 166 | Karnataka | 88 | 88 | 0 | Available | VTL Infra | 57L | Low
Project 167 | Punjab | 93 | 94 | -1 | Available | XYZ | 24L | Medium
Project 168 | Madhya Pradesh | 83 | 72 | 11 | Shortage | Apex | 45L | High
Project 169 | Uttar Pradesh | 77 | 76 | 1 | Shortage | RST | 85L | Critical
Project 170 | Punjab | 69 | 70 | -1 | Available | PQR | 45L | Low
Project 171 | Ladakh | 73 | 70 | 3 | Delayed | Sigma | 34L | Medium
Project 172 | Delhi | 69 | 55 | 14 | Partially Available | Sigma | 23L | Medium
Project 173 | West Bengal | 84 | 55 | 29 | Delayed | Sigma | 69L | High
Project 174 | Bihar | 62 | 61 | 1 | Available | VTL Infra | 76L | Medium
Project 175 | West Bengal | 82 | 75 | 7 | Delayed | Sigma | 28L | Medium
Project 176 | Arunachal Pradesh | 76 | 79 | -3 | Available | Apex | 32L | Low
Project 177 | Madhya Pradesh | 67 | 46 | 21 | Delayed | LMN | 36L | Medium
Project 178 | Assam | 64 | 62 | 2 | Shortage | PQR | 27L | Critical
Project 179 | Jharkhand | 84 | 71 | 13 | Delayed | Nexus | 90L | Low
Project 180 | Karnataka | 95 | 95 | 0 | Available | RST | 56L | Low
Project 181 | West Bengal | 58 | 55 | 3 | Delayed | VTL Infra | 25L | Medium
Project 182 | Ladakh | 59 | 54 | 5 | Shortage | Nexus | 77L | Critical
Project 183 | Arunachal Pradesh | 57 | 60 | -3 | Available | Prime EPC | 95L | Low
Project 184 | Arunachal Pradesh | 64 | 41 | 23 | Available | XYZ | 61L | Medium
Project 185 | Telangana | 96 | 94 | 2 | Shortage | Apex | 85L | Medium
Project 186 | Jharkhand | 65 | 64 | 1 | Delayed | ABC | 94L | High
Project 187 | Jharkhand | 59 | 60 | -1 | Available | PQR | 95L | Low
Project 188 | Telangana | 60 | 54 | 6 | Partially Available | PQR | 68L | Medium
Project 189 | Bihar | 60 | 60 | 0 | Available | Apex | 34L | Low
Project 190 | Jharkhand | 96 | 84 | 12 | Delayed | LMN | 41L | Medium
Project 191 | Ladakh | 86 | 84 | 2 | Available | Apex | 30L | Low
Project 192 | Rajasthan | 88 | 94 | -6 | Partially Available | Sigma | 94L | High
Project 193 | Uttar Pradesh | 65 | 67 | -2 | Delayed | Prime EPC | 39L | High
Project 194 | Haryana | 81 | 83 | -2 | Available | Prime EPC | 54L | Low
Project 195 | Karnataka | 89 | 92 | -3 | Delayed | VTL Infra | 42L | Low
Project 196 | Gujarat | 83 | 82 | 1 | Shortage | PQR | 71L | Critical
Project 197 | Madhya Pradesh | 93 | 92 | 1 | Available | Apex | 65L | Low
Project 198 | Rajasthan | 88 | 68 | 20 | Available | Apex | 75L | High
Project 199 | Uttar Pradesh | 82 | 86 | -4 | Shortage | Sigma | 21L | Medium
Project 200 | Jharkhand | 80 | 73 | 7 | Delayed | ABC | 46L | Medium

## Reference
Prompt
Analyze this EPC project tracker and identify the 10 most important management insights. Do not simply summarize the data. Look for exceptions, delays, cost risks, vendor problems and projects requiring immediate attention.