## Project WBS
WBS | Task Name | Duration | Start Date | Finish Date | Resource Name | % Complete
1 | Project Initiation & Engineering | 40 | 2026-01-05 | 2026-02-13 | Project Management Team | 57
1.1 | Project Kick-off | 3 | 2026-01-05 | 2026-01-07 | QA/QC Engineer | 35
1.2 | Contract Review | 6 | 2026-01-06 | 2026-01-11 | Subcontractor Team | 75
1.3 | Scope Confirmation | 3 | 2026-01-09 | 2026-01-11 | HSE Officer | 20
1.4 | Project Execution Plan | 10 | 2026-01-10 | 2026-01-19 | Commercial Team | 40
1.5 | Site Survey | 6 | 2026-01-15 | 2026-01-20 | Subcontractor Team | 60
1.6 | Topographical Survey | 7 | 2026-01-18 | 2026-01-24 | Commercial Team | 90
1.7 | Route Survey | 5 | 2026-01-21 | 2026-01-25 | Commercial Team | 90
1.8 | Utility Survey | 6 | 2026-01-23 | 2026-01-28 | Procurement Engineer | 50
1.9 | Geotechnical Investigation | 2 | 2026-01-26 | 2026-01-27 | Planning Engineer | 70
1.10 | Design Basis | 3 | 2026-01-27 | 2026-01-29 | Subcontractor Team | 25
1.11 | Basic Engineering | 3 | 2026-01-28 | 2026-01-30 | Project Manager | 50
1.12 | Detailed Engineering | 9 | 2026-01-29 | 2026-02-06 | Site Engineer | 75
1.13 | Design Review | 3 | 2026-02-02 | 2026-02-04 | Civil Engineer | 40
1.14 | Client Approval | 7 | 2026-02-03 | 2026-02-09 | Commercial Team | 35
1.15 | Engineering Change Management | 8 | 2026-02-06 | 2026-02-13 | QA/QC Engineer | 80
1.16 | Document Control | 3 | 2026-02-10 | 2026-02-12 | Site Engineer | 80
2 | Procurement & Vendor Management | 91 | 2026-02-11 | 2026-05-12 | Project Management Team | 50
2.1 | Procurement Plan | 6 | 2026-02-11 | 2026-02-16 | QA/QC Engineer | 60
2.2 | Vendor Prequalification | 6 | 2026-02-14 | 2026-02-19 | Electrical Engineer | 25
2.3 | RFQ Preparation | 4 | 2026-02-17 | 2026-02-20 | Document Controller | 75
2.4 | RFQ Issue | 6 | 2026-02-19 | 2026-02-24 | Subcontractor Team | 0
2.5 | Technical Bid Evaluation | 7 | 2026-02-22 | 2026-02-28 | Electrical Engineer | 35
2.6 | Commercial Bid Evaluation | 8 | 2026-02-25 | 2026-03-04 | Fiber Installation Team | 0
2.7 | Vendor Finalization | 10 | 2026-03-01 | 2026-03-10 | Subcontractor Team | 50
2.8 | Purchase Order Release | 3 | 2026-03-06 | 2026-03-08 | QA/QC Engineer | 40
2.9 | Cable Raw Material Procurement | 17 | 2026-03-07 | 2026-03-23 | Subcontractor Team | 90
2.10 | Optical Fiber Procurement | 14 | 2026-03-15 | 2026-03-28 | Fiber Installation Team | 50
2.11 | HDPE Duct Procurement | 13 | 2026-03-22 | 2026-04-03 | Subcontractor Team | 25
2.12 | Joint Closure Procurement | 11 | 2026-03-28 | 2026-04-07 | Electrical Engineer | 70
2.13 | Fiber Accessories Procurement | 13 | 2026-04-02 | 2026-04-14 | Commercial Team | 60
2.14 | Electrical Materials Procurement | 5 | 2026-04-08 | 2026-04-12 | Procurement Engineer | 70
2.15 | Earthing Materials Procurement | 17 | 2026-04-10 | 2026-04-26 | Subcontractor Team | 10
2.16 | PPE Procurement | 5 | 2026-04-18 | 2026-04-22 | QA/QC Engineer | 80
2.17 | Inspection & Test Plan | 2 | 2026-04-20 | 2026-04-21 | HSE Officer | 80
2.18 | Vendor Inspection | 5 | 2026-04-21 | 2026-04-25 | Design Engineer | 50
2.19 | Factory Acceptance Test | 9 | 2026-04-23 | 2026-05-01 | Subcontractor Team | 20
2.20 | Material Dispatch | 3 | 2026-04-27 | 2026-04-29 | Document Controller | 75
2.21 | Material Receipt | 9 | 2026-04-28 | 2026-05-06 | Electrical Engineer | 75
2.22 | Material Inspection | 6 | 2026-05-02 | 2026-05-07 | QA/QC Engineer | 25
2.23 | Material Storage | 8 | 2026-05-05 | 2026-05-12 | Civil Engineer | 75
3 | Civil & Site Preparation | 95 | 2026-05-09 | 2026-08-11 | Project Management Team | 56
3.1 | Site Mobilization | 10 | 2026-05-09 | 2026-05-18 | Testing & Commissioning Team | 90
3.2 | Site Office Setup | 10 | 2026-05-14 | 2026-05-23 | Electrical Engineer | 80
3.3 | Temporary Power Arrangement | 8 | 2026-05-19 | 2026-05-26 | Procurement Engineer | 40
3.4 | Temporary Water Arrangement | 6 | 2026-05-23 | 2026-05-28 | Civil Engineer | 100
3.5 | Site Barricading | 2 | 2026-05-26 | 2026-05-27 | Design Engineer | 0
3.6 | Safety Signage | 9 | 2026-05-27 | 2026-06-04 | QA/QC Engineer | 90
3.7 | Access Road Preparation | 9 | 2026-05-31 | 2026-06-08 | Procurement Engineer | 35
3.8 | Survey Benchmark Establishment | 4 | 2026-06-04 | 2026-06-07 | Electrical Engineer | 80
3.9 | Excavation Marking | 9 | 2026-06-06 | 2026-06-14 | Commercial Team | 60
3.10 | Trench Excavation | 9 | 2026-06-10 | 2026-06-18 | Fiber Installation Team | 90
3.11 | Road Crossing Preparation | 10 | 2026-06-14 | 2026-06-23 | Project Manager | 75
3.12 | Duct Bank Excavation | 6 | 2026-06-19 | 2026-06-24 | Electrical Engineer | 35
3.13 | Sand Bedding | 3 | 2026-06-22 | 2026-06-24 | Document Controller | 50
3.14 | Duct Installation | 16 | 2026-06-23 | 2026-07-08 | QA/QC Engineer | 90
3.15 | Duct Jointing | 6 | 2026-07-01 | 2026-07-06 | Design Engineer | 50
3.16 | Warning Tape Installation | 11 | 2026-07-04 | 2026-07-14 | Document Controller | 100
3.17 | Backfilling | 9 | 2026-07-09 | 2026-07-17 | Testing & Commissioning Team | 0
3.18 | Compaction | 6 | 2026-07-13 | 2026-07-18 | Site Engineer | 50
3.19 | Manhole Construction | 6 | 2026-07-16 | 2026-07-21 | Document Controller | 20
3.20 | Handhole Construction | 18 | 2026-07-19 | 2026-08-05 | Design Engineer | 40
3.21 | Foundation Works | 9 | 2026-07-28 | 2026-08-05 | Planning Engineer | 0
3.22 | Restoration of Road Surface | 2 | 2026-08-01 | 2026-08-02 | HSE Officer | 50
3.23 | Site Drainage | 10 | 2026-08-02 | 2026-08-11 | Planning Engineer | 100
3.24 | Civil Snag Rectification | 5 | 2026-08-07 | 2026-08-11 | Planning Engineer | 20
4 | Cable & Network Installation | 92 | 2026-08-09 | 2026-11-08 | Project Management Team | 47
4.1 | Cable Drum Inspection | 6 | 2026-08-09 | 2026-08-14 | Commercial Team | 0
4.2 | Cable Drum Handling | 10 | 2026-08-12 | 2026-08-21 | Testing & Commissioning Team | 0
4.3 | Cable Route Preparation | 7 | 2026-08-17 | 2026-08-23 | Project Manager | 0
4.4 | Cable Pulling Plan | 7 | 2026-08-20 | 2026-08-26 | HSE Officer | 0
4.5 | Optical Fiber Cable Pulling | 9 | 2026-08-23 | 2026-08-31 | Document Controller | 0
4.6 | Power Cable Pulling | 4 | 2026-08-27 | 2026-08-30 | Procurement Engineer | 0
4.7 | Control Cable Pulling | 9 | 2026-08-29 | 2026-09-06 | Design Engineer | 0
4.8 | Cable Blowing | 10 | 2026-09-02 | 2026-09-11 | Planning Engineer | 0
4.9 | Cable Dressing | 8 | 2026-09-07 | 2026-09-14 | Design Engineer | 0
4.10 | Cable Identification | 4 | 2026-09-11 | 2026-09-14 | Commercial Team | 0
4.11 | Cable Tagging | 6 | 2026-09-13 | 2026-09-18 | Fiber Installation Team | 0
4.12 | Joint Pit Preparation | 8 | 2026-09-16 | 2026-09-23 | Design Engineer | 0
4.13 | Joint Closure Installation | 13 | 2026-09-20 | 2026-10-02 | Procurement Engineer | 0
4.14 | Fiber Splicing | 8 | 2026-09-26 | 2026-10-03 | Planning Engineer | 0
4.15 | Splice Tray Installation | 11 | 2026-09-30 | 2026-10-10 | Project Manager | 0
4.16 | OTDR Testing | 4 | 2026-10-05 | 2026-10-08 | Site Engineer | 0
4.17 | Power Meter Testing | 2 | 2026-10-07 | 2026-10-08 | QA/QC Engineer | 0
4.18 | Link Loss Testing | 5 | 2026-10-08 | 2026-10-12 | Testing & Commissioning Team | 0
4.19 | Cable Termination | 6 | 2026-10-10 | 2026-10-15 | Site Engineer | 0
4.20 | ODF Installation | 6 | 2026-10-13 | 2026-10-18 | Electrical Engineer | 0
4.21 | Patch Panel Installation | 14 | 2026-10-16 | 2026-10-29 | Commercial Team | 0
4.22 | Rack Installation | 7 | 2026-10-23 | 2026-10-29 | HSE Officer | 0
4.23 | Network Equipment Installation | 13 | 2026-10-26 | 2026-11-07 | Fiber Installation Team | 0
4.24 | Equipment Earthing | 7 | 2026-11-01 | 2026-11-07 | HSE Officer | 0
4.25 | Cable Management | 5 | 2026-11-04 | 2026-11-08 | Document Controller | 0
4.26 | Labeling & Identification | 3 | 2026-11-06 | 2026-11-08 | Fiber Installation Team | 0
4.27 | As-Built Route Verification | 2 | 2026-11-07 | 2026-11-08 | Testing & Commissioning Team | 0
5 | Electrical & Auxiliary Systems | 77 | 2026-11-08 | 2027-01-23 | Project Management Team | 0
5.1 | Electrical Load Assessment | 3 | 2026-11-08 | 2026-11-10 | Testing & Commissioning Team | 0
5.2 | LT Panel Installation | 13 | 2026-11-09 | 2026-11-21 | Project Manager | 0
5.3 | Distribution Board Installation | 12 | 2026-11-15 | 2026-11-26 | Commercial Team | 0
5.4 | UPS Installation | 15 | 2026-11-21 | 2026-12-05 | Electrical Engineer | 0
5.5 | Battery Bank Installation | 16 | 2026-11-28 | 2026-12-13 | Project Manager | 0
5.6 | Lighting Installation | 7 | 2026-12-06 | 2026-12-12 | QA/QC Engineer | 0
5.7 | Small Power Installation | 8 | 2026-12-09 | 2026-12-16 | QA/QC Engineer | 0
5.8 | Earthing Grid Installation | 7 | 2026-12-13 | 2026-12-19 | Testing & Commissioning Team | 0
5.9 | Equipment Earthing | 4 | 2026-12-16 | 2026-12-19 | Civil Engineer | 0
5.10 | Lightning Protection | 8 | 2026-12-18 | 2026-12-25 | Fiber Installation Team | 0
5.11 | Cable Tray Installation | 18 | 2026-12-22 | 2027-01-08 | Fiber Installation Team | 0
5.12 | Cable Tray Earthing | 6 | 2026-12-31 | 2027-01-05 | Site Engineer | 0
5.13 | Control Panel Installation | 7 | 2027-01-03 | 2027-01-09 | Electrical Engineer | 0
5.14 | Auxiliary Cable Termination | 9 | 2027-01-06 | 2027-01-14 | Subcontractor Team | 0
5.15 | Electrical Continuity Test | 8 | 2027-01-10 | 2027-01-17 | Electrical Engineer | 0
5.16 | Insulation Resistance Test | 4 | 2027-01-14 | 2027-01-17 | QA/QC Engineer | 0
5.17 | Functional Testing | 5 | 2027-01-16 | 2027-01-20 | Planning Engineer | 0
5.18 | Electrical Safety Inspection | 6 | 2027-01-18 | 2027-01-23 | QA/QC Engineer | 0
6 | Testing & Commissioning | 50 | 2027-01-21 | 2027-03-11 | Project Management Team | 0
6.1 | Commissioning Plan | 6 | 2027-01-21 | 2027-01-26 | Planning Engineer | 0
6.2 | Pre-Commissioning Inspection | 3 | 2027-01-24 | 2027-01-26 | Project Manager | 0
6.3 | Mechanical Completion | 3 | 2027-01-25 | 2027-01-27 | Testing & Commissioning Team | 0
6.4 | Installation Quality Audit | 10 | 2027-01-26 | 2027-02-04 | QA/QC Engineer | 0
6.5 | Fiber Continuity Test | 4 | 2027-01-31 | 2027-02-03 | Site Engineer | 0
6.6 | OTDR Baseline Test | 4 | 2027-02-02 | 2027-02-05 | QA/QC Engineer | 0
6.7 | End-to-End Fiber Test | 10 | 2027-02-04 | 2027-02-13 | Planning Engineer | 0
6.8 | Cable Attenuation Test | 6 | 2027-02-09 | 2027-02-14 | Commercial Team | 0
6.9 | Power System Testing | 6 | 2027-02-12 | 2027-02-17 | Procurement Engineer | 0
6.10 | Protection System Testing | 6 | 2027-02-15 | 2027-02-20 | HSE Officer | 0
6.11 | UPS Functional Test | 6 | 2027-02-18 | 2027-02-23 | QA/QC Engineer | 0
6.12 | Battery Performance Test | 4 | 2027-02-21 | 2027-02-24 | Commercial Team | 0
6.13 | Network Equipment Configuration | 6 | 2027-02-23 | 2027-02-28 | Fiber Installation Team | 0
6.14 | Network Connectivity Test | 4 | 2027-02-26 | 2027-03-01 | Testing & Commissioning Team | 0
6.15 | Alarm Verification | 2 | 2027-02-28 | 2027-03-01 | Site Engineer | 0
6.16 | SCADA/Monitoring Integration | 4 | 2027-03-01 | 2027-03-04 | Testing & Commissioning Team | 0
6.17 | Integrated System Testing | 2 | 2027-03-03 | 2027-03-04 | Site Engineer | 0
6.18 | Performance Test | 6 | 2027-03-04 | 2027-03-09 | Subcontractor Team | 0
6.19 | Reliability Run | 3 | 2027-03-07 | 2027-03-09 | Site Engineer | 0
6.20 | Test Report Compilation | 4 | 2027-03-08 | 2027-03-11 | Civil Engineer | 0
7 | HSE & Quality Management | 42 | 2027-03-10 | 2027-04-20 | Project Management Team | 0
7.1 | Project HSE Plan | 3 | 2027-03-10 | 2027-03-12 | Fiber Installation Team | 0
7.2 | Risk Assessment | 4 | 2027-03-11 | 2027-03-14 | Project Manager | 0
7.3 | Method Statement Approval | 2 | 2027-03-13 | 2027-03-14 | Procurement Engineer | 0
7.4 | Toolbox Talks | 2 | 2027-03-14 | 2027-03-15 | Planning Engineer | 0
7.5 | Daily Safety Inspection | 2 | 2027-03-15 | 2027-03-16 | QA/QC Engineer | 0
7.6 | Weekly HSE Audit | 6 | 2027-03-16 | 2027-03-21 | Site Engineer | 0
7.7 | Permit to Work Management | 7 | 2027-03-19 | 2027-03-25 | Electrical Engineer | 0
7.8 | Environmental Monitoring | 2 | 2027-03-22 | 2027-03-23 | Site Engineer | 0
7.9 | Waste Management | 5 | 2027-03-23 | 2027-03-27 | Electrical Engineer | 0
7.10 | Emergency Preparedness Drill | 8 | 2027-03-25 | 2027-04-01 | Planning Engineer | 0
7.11 | Quality Plan | 7 | 2027-03-29 | 2027-04-04 | QA/QC Engineer | 0
7.12 | Inspection Request Management | 4 | 2027-04-01 | 2027-04-04 | Civil Engineer | 0
7.13 | Material Test Certificate Review | 4 | 2027-04-03 | 2027-04-06 | Document Controller | 0
7.14 | NCR Management | 8 | 2027-04-05 | 2027-04-12 | Civil Engineer | 0
7.15 | Corrective Action Tracking | 7 | 2027-04-09 | 2027-04-15 | Document Controller | 0
7.16 | Quality Audit | 2 | 2027-04-12 | 2027-04-13 | Commercial Team | 0
7.17 | Final Quality Dossier | 8 | 2027-04-13 | 2027-04-20 | HSE Officer | 0
8 | Documentation & Handover | 63 | 2027-04-17 | 2027-06-18 | Project Management Team | 0
8.1 | Document Index Preparation | 2 | 2027-04-17 | 2027-04-18 | Site Engineer | 0
8.2 | Drawing Register | 5 | 2027-04-18 | 2027-04-22 | Project Manager | 0
8.3 | Approved for Construction Drawings | 16 | 2027-04-20 | 2027-05-05 | Design Engineer | 0
8.4 | As-Built Drawings | 3 | 2027-04-28 | 2027-04-30 | Project Manager | 0
8.5 | Cable Schedule | 4 | 2027-04-29 | 2027-05-02 | Site Engineer | 0
8.6 | Equipment Schedule | 6 | 2027-05-01 | 2027-05-06 | Fiber Installation Team | 0
8.7 | Test Certificates | 4 | 2027-05-04 | 2027-05-07 | Fiber Installation Team | 0
8.8 | Inspection Records | 5 | 2027-05-06 | 2027-05-10 | Procurement Engineer | 0
8.9 | Material Reconciliation | 8 | 2027-05-08 | 2027-05-15 | Procurement Engineer | 0
8.10 | Warranty Documents | 4 | 2027-05-12 | 2027-05-15 | QA/QC Engineer | 0
8.11 | O&M Manual | 2 | 2027-05-14 | 2027-05-15 | Document Controller | 0
8.12 | Spare Parts List | 10 | 2027-05-15 | 2027-05-24 | QA/QC Engineer | 0
8.13 | Training Material | 8 | 2027-05-20 | 2027-05-27 | Commercial Team | 0
8.14 | Operator Training | 4 | 2027-05-24 | 2027-05-27 | Project Manager | 0
8.15 | Maintenance Training | 2 | 2027-05-26 | 2027-05-27 | QA/QC Engineer | 0
8.16 | Client Walkdown | 9 | 2027-05-27 | 2027-06-04 | Civil Engineer | 0
8.17 | Punch List Preparation | 7 | 2027-05-31 | 2027-06-06 | Testing & Commissioning Team | 0
8.18 | Punch List Closure | 3 | 2027-06-03 | 2027-06-05 | Design Engineer | 0
8.19 | Final Handover Dossier | 10 | 2027-06-04 | 2027-06-13 | Testing & Commissioning Team | 0
8.20 | Taking Over Certificate | 10 | 2027-06-09 | 2027-06-18 | Civil Engineer | 0
9 | Project Closure | 52 | 2027-06-14 | 2027-08-04 | Project Management Team | 0
9.1 | Final Quantity Reconciliation | 7 | 2027-06-14 | 2027-06-20 | QA/QC Engineer | 0
9.2 | Final Measurement | 7 | 2027-06-17 | 2027-06-23 | Testing & Commissioning Team | 0
9.3 | Final Invoice Preparation | 2 | 2027-06-20 | 2027-06-21 | Procurement Engineer | 0
9.4 | Commercial Closure | 9 | 2027-06-21 | 2027-06-29 | Procurement Engineer | 0
9.5 | Subcontractor Closure | 10 | 2027-06-25 | 2027-07-04 | Design Engineer | 0
9.6 | Vendor Closure | 8 | 2027-06-30 | 2027-07-07 | Site Engineer | 0
9.7 | Site Demobilization | 5 | 2027-07-04 | 2027-07-08 | Subcontractor Team | 0
9.8 | Temporary Facility Removal | 6 | 2027-07-06 | 2027-07-11 | Subcontractor Team | 0
9.9 | Excess Material Return | 5 | 2027-07-09 | 2027-07-13 | Site Engineer | 0
9.10 | Lessons Learned Workshop | 9 | 2027-07-11 | 2027-07-19 | Electrical Engineer | 0
9.11 | Project Performance Review | 6 | 2027-07-15 | 2027-07-20 | Electrical Engineer | 0
9.12 | Final Cost Report | 6 | 2027-07-18 | 2027-07-23 | Design Engineer | 0
9.13 | Final Schedule Report | 8 | 2027-07-21 | 2027-07-28 | Electrical Engineer | 0
9.14 | Management Review | 2 | 2027-07-25 | 2027-07-26 | Subcontractor Team | 0
9.15 | Project Closure Report | 10 | 2027-07-26 | 2027-08-04 | Fiber Installation Team | 0
9.16 | Archive Project Records | 2 | 2027-07-31 | 2027-08-01 | Design Engineer | 0

## Instructions
Vindhya Telelinks Ltd. – Project WBS Practice Dataset
Purpose | Practice WBS, scheduling, resource allocation and % completion analysis in MS Excel / MS Project.
Records | 190 WBS rows including phase summary tasks.
Project Type | Telecom / EPC project – engineering, procurement, civil works, cable installation, testing and handover.
Columns | WBS, Task Name, Duration, Start Date, Finish Date, Resource Name, % Complete
Suggested Exercises | Create Gantt Chart, identify delayed tasks, resource-wise workload, phase-wise completion and project progress dashboard.