## Project WBS
WBS | Task Name | Duration | Start Date | Finish Date | Resource Name | % Complete
1 | Project Initiation & Engineering | 40 | 2026-01-05 | 2026-02-13 | Project Management Team | 57
1.1 | Project Kick-off | 3 | 2026-01-05 | 2026-01-07 | QA/QC Engineer | 35
1.2 | Contract Review | 6 | 2026-01-06 | 2026-01-11 | Subcontractor Team | 75
1.3 | Scope Confirmation | 3 | 2026-01-09 | 2026-01-11 | HSE Officer | 20
1.4 | Project Execution Plan | 10 | 2026-01-10 | 2026-01-19 | Commercial Team | 40
1.5 | Site Survey | 6 | 2026-01-15 | 2026-01-20 | Subcontractor Team | 60
1.6 | Topographical Survey | 7 | 2026-01-18 | 2026-01-24 | Commercial Team | 90
1.7 | Route Survey | 5 | 2026-01-21 | 2026-01-25 | Commercial Team | 90
1.8 | Utility Survey | 6 | 2026-01-23 | 2026-01-28 | Procurement Engineer | 50
1.9 | Geotechnical Investigation | 2 | 2026-01-26 | 2026-01-27 | Planning Engineer | 70
1.10 | Design Basis | 3 | 2026-01-27 | 2026-01-29 | Subcontractor Team | 25
1.11 | Basic Engineering | 3 | 2026-01-28 | 2026-01-30 | Project Manager | 50
1.12 | Detailed Engineering | 9 | 2026-01-29 | 2026-02-06 | Site Engineer | 75
1.13 | Design Review | 3 | 2026-02-02 | 2026-02-04 | Civil Engineer | 40
1.14 | Client Approval | 7 | 2026-02-03 | 2026-02-09 | Commercial Team | 35
1.15 | Engineering Change Management | 8 | 2026-02-06 | 2026-02-13 | QA/QC Engineer | 80
1.16 | Document Control | 3 | 2026-02-10 | 2026-02-12 | Site Engineer | 80
2 | Procurement & Vendor Management | 91 | 2026-02-11 | 2026-05-12 | Project Management Team | 50
2.1 | Procurement Plan | 6 | 2026-02-11 | 2026-02-16 | QA/QC Engineer | 60
2.2 | Vendor Prequalification | 6 | 2026-02-14 | 2026-02-19 | Electrical Engineer | 25
2.3 | RFQ Preparation | 4 | 2026-02-17 | 2026-02-20 | Document Controller | 75
2.4 | RFQ Issue | 6 | 2026-02-19 | 2026-02-24 | Subcontractor Team | 0
2.5 | Technical Bid Evaluation | 7 | 2026-02-22 | 2026-02-28 | Electrical Engineer | 35
2.6 | Commercial Bid Evaluation | 8 | 2026-02-25 | 2026-03-04 | Fiber Installation Team | 0
2.7 | Vendor Finalization | 10 | 2026-03-01 | 2026-03-10 | Subcontractor Team | 50
2.8 | Purchase Order Release | 3 | 2026-03-06 | 2026-03-08 | QA/QC Engineer | 40
2.9 | Cable Raw Material Procurement | 17 | 2026-03-07 | 2026-03-23 | Subcontractor Team | 90
2.10 | Optical Fiber Procurement | 14 | 2026-03-15 | 2026-03-28 | Fiber Installation Team | 50
2.11 | HDPE Duct Procurement | 13 | 2026-03-22 | 2026-04-03 | Subcontractor Team | 25
2.12 | Joint Closure Procurement | 11 | 2026-03-28 | 2026-04-07 | Electrical Engineer | 70
2.13 | Fiber Accessories Procurement | 13 | 2026-04-02 | 2026-04-14 | Commercial Team | 60
2.14 | Electrical Materials Procurement | 5 | 2026-04-08 | 2026-04-12 | Procurement Engineer | 70
2.15 | Earthing Materials Procurement | 17 | 2026-04-10 | 2026-04-26 | Subcontractor Team | 10
2.16 | PPE Procurement | 5 | 2026-04-18 | 2026-04-22 | QA/QC Engineer | 80
2.17 | Inspection & Test Plan | 2 | 2026-04-20 | 2026-04-21 | HSE Officer | 80
2.18 | Vendor Inspection | 5 | 2026-04-21 | 2026-04-25 | Design Engineer | 50
2.19 | Factory Acceptance Test | 9 | 2026-04-23 | 2026-05-01 | Subcontractor Team | 20
2.20 | Material Dispatch | 3 | 2026-04-27 | 2026-04-29 | Document Controller | 75
2.21 | Material Receipt | 9 | 2026-04-28 | 2026-05-06 | Electrical Engineer | 75
2.22 | Material Inspection | 6 | 2026-05-02 | 2026-05-07 | QA/QC Engineer | 25
2.23 | Material Storage | 8 | 2026-05-05 | 2026-05-12 | Civil Engineer | 75
3 | Civil & Site Preparation | 95 | 2026-05-09 | 2026-08-11 | Project Management Team | 56
3.1 | Site Mobilization | 10 | 2026-05-09 | 2026-05-18 | Testing & Commissioning Team | 90
3.2 | Site Office Setup | 10 | 2026-05-14 | 2026-05-23 | Electrical Engineer | 80
3.3 | Temporary Power Arrangement | 8 | 2026-05-19 | 2026-05-26 | Procurement Engineer | 40
3.4 | Temporary Water Arrangement | 6 | 2026-05-23 | 2026-05-28 | Civil Engineer | 100
3.5 | Site Barricading | 2 | 2026-05-26 | 2026-05-27 | Design Engineer | 0
3.6 | Safety Signage | 9 | 2026-05-27 | 2026-06-04 | QA/QC Engineer | 90
3.7 | Access Road Preparation | 9 | 2026-05-31 | 2026-06-08 | Procurement Engineer | 35
3.8 | Survey Benchmark Establishment | 4 | 2026-06-04 | 2026-06-07 | Electrical Engineer | 80
3.9 | Excavation Marking | 9 | 2026-06-06 | 2026-06-14 | Commercial Team | 60
3.10 | Trench Excavation | 9 | 2026-06-10 | 2026-06-18 | Fiber Installation Team | 90
3.11 | Road Crossing Preparation | 10 | 2026-06-14 | 2026-06-23 | Project Manager | 75
3.12 | Duct Bank Excavation | 6 | 2026-06-19 | 2026-06-24 | Electrical Engineer | 35
3.13 | Sand Bedding | 3 | 2026-06-22 | 2026-06-24 | Document Controller | 50
3.14 | Duct Installation | 16 | 2026-06-23 | 2026-07-08 | QA/QC Engineer | 90
3.15 | Duct Jointing | 6 | 2026-07-01 | 2026-07-06 | Design Engineer | 50
3.16 | Warning Tape Installation | 11 | 2026-07-04 | 2026-07-14 | Document Controller | 100
3.17 | Backfilling | 9 | 2026-07-09 | 2026-07-17 | Testing & Commissioning Team | 0
3.18 | Compaction | 6 | 2026-07-13 | 2026-07-18 | Site Engineer | 50
3.19 | Manhole Construction | 6 | 2026-07-16 | 2026-07-21 | Document Controller | 20
3.20 | Handhole Construction | 18 | 2026-07-19 | 2026-08-05 | Design Engineer | 40
3.21 | Foundation Works | 9 | 2026-07-28 | 2026-08-05 | Planning Engineer | 0
3.22 | Restoration of Road Surface | 2 | 2026-08-01 | 2026-08-02 | HSE Officer | 50
3.23 | Site Drainage | 10 | 2026-08-02 | 2026-08-11 | Planning Engineer | 100
3.24 | Civil Snag Rectification | 5 | 2026-08-07 | 2026-08-11 | Planning Engineer | 20
4 | Cable & Network Installation | 92 | 2026-08-09 | 2026-11-08 | Project Management Team | 47
4.1 | Cable Drum Inspection | 6 | 2026-08-09 | 2026-08-14 | Commercial Team | 0
4.2 | Cable Drum Handling | 10 | 2026-08-12 | 2026-08-21 | Testing & Commissioning Team | 25
4.3 | Cable Route Preparation | 7 | 2026-08-17 | 2026-08-23 | Project Manager | 10
4.4 | Cable Pulling Plan | 7 | 2026-08-20 | 2026-08-26 | HSE Officer | 75
4.5 | Optical Fiber Cable Pulling | 9 | 2026-08-23 | 2026-08-31 | Document Controller | 80
4.6 | Power Cable Pulling | 4 | 2026-08-27 | 2026-08-30 | Procurement Engineer | 60
4.7 | Control Cable Pulling | 9 | 2026-08-29 | 2026-09-06 | Design Engineer | 70
4.8 | Cable Blowing | 10 | 2026-09-02 | 2026-09-11 | Planning Engineer | 25
4.9 | Cable Dressing | 8 | 2026-09-07 | 2026-09-14 | Design Engineer | 75
4.10 | Cable Identification | 4 | 2026-09-11 | 2026-09-14 | Commercial Team | 90
4.11 | Cable Tagging | 6 | 2026-09-13 | 2026-09-18 | Fiber Installation Team | 60
4.12 | Joint Pit Preparation | 8 | 2026-09-16 | 2026-09-23 | Design Engineer | 90
4.13 | Joint Closure Installation | 13 | 2026-09-20 | 2026-10-02 | Procurement Engineer | 90
4.14 | Fiber Splicing | 8 | 2026-09-26 | 2026-10-03 | Planning Engineer | 0
4.15 | Splice Tray Installation | 11 | 2026-09-30 | 2026-10-10 | Project Manager | 0
4.16 | OTDR Testing | 4 | 2026-10-05 | 2026-10-08 | Site Engineer | 75
4.17 | Power Meter Testing | 2 | 2026-10-07 | 2026-10-08 | QA/QC Engineer | 0
4.18 | Link Loss Testing | 5 | 2026-10-08 | 2026-10-12 | Testing & Commissioning Team | 35
4.19 | Cable Termination | 6 | 2026-10-10 | 2026-10-15 | Site Engineer | 50
4.20 | ODF Installation | 6 | 2026-10-13 | 2026-10-18 | Electrical Engineer | 50
4.21 | Patch Panel Installation | 14 | 2026-10-16 | 2026-10-29 | Commercial Team | 70
4.22 | Rack Installation | 7 | 2026-10-23 | 2026-10-29 | HSE Officer | 10
4.23 | Network Equipment Installation | 13 | 2026-10-26 | 2026-11-07 | Fiber Installation Team | 20
4.24 | Equipment Earthing | 7 | 2026-11-01 | 2026-11-07 | HSE Officer | 50
4.25 | Cable Management | 5 | 2026-11-04 | 2026-11-08 | Document Controller | 75
4.26 | Labeling & Identification | 3 | 2026-11-06 | 2026-11-08 | Fiber Installation Team | 60
4.27 | As-Built Route Verification | 2 | 2026-11-07 | 2026-11-08 | Testing & Commissioning Team | 20
5 | Electrical & Auxiliary Systems | 77 | 2026-11-08 | 2027-01-23 | Project Management Team | 50
5.1 | Electrical Load Assessment | 3 | 2026-11-08 | 2026-11-10 | Testing & Commissioning Team | 0
5.2 | LT Panel Installation | 13 | 2026-11-09 | 2026-11-21 | Project Manager | 100
5.3 | Distribution Board Installation | 12 | 2026-11-15 | 2026-11-26 | Commercial Team | 100
5.4 | UPS Installation | 15 | 2026-11-21 | 2026-12-05 | Electrical Engineer | 20
5.5 | Battery Bank Installation | 16 | 2026-11-28 | 2026-12-13 | Project Manager | 75
5.6 | Lighting Installation | 7 | 2026-12-06 | 2026-12-12 | QA/QC Engineer | 75
5.7 | Small Power Installation | 8 | 2026-12-09 | 2026-12-16 | QA/QC Engineer | 90
5.8 | Earthing Grid Installation | 7 | 2026-12-13 | 2026-12-19 | Testing & Commissioning Team | 10
5.9 | Equipment Earthing | 4 | 2026-12-16 | 2026-12-19 | Civil Engineer | 40
5.10 | Lightning Protection | 8 | 2026-12-18 | 2026-12-25 | Fiber Installation Team | 60
5.11 | Cable Tray Installation | 18 | 2026-12-22 | 2027-01-08 | Fiber Installation Team | 0
5.12 | Cable Tray Earthing | 6 | 2026-12-31 | 2027-01-05 | Site Engineer | 10
5.13 | Control Panel Installation | 7 | 2027-01-03 | 2027-01-09 | Electrical Engineer | 25
5.14 | Auxiliary Cable Termination | 9 | 2027-01-06 | 2027-01-14 | Subcontractor Team | 90
5.15 | Electrical Continuity Test | 8 | 2027-01-10 | 2027-01-17 | Electrical Engineer | 25
5.16 | Insulation Resistance Test | 4 | 2027-01-14 | 2027-01-17 | QA/QC Engineer | 35
5.17 | Functional Testing | 5 | 2027-01-16 | 2027-01-20 | Planning Engineer | 50
5.18 | Electrical Safety Inspection | 6 | 2027-01-18 | 2027-01-23 | QA/QC Engineer | 90
6 | Testing & Commissioning | 50 | 2027-01-21 | 2027-03-11 | Project Management Team | 42
6.1 | Commissioning Plan | 6 | 2027-01-21 | 2027-01-26 | Planning Engineer | 100
6.2 | Pre-Commissioning Inspection | 3 | 2027-01-24 | 2027-01-26 | Project Manager | 20
6.3 | Mechanical Completion | 3 | 2027-01-25 | 2027-01-27 | Testing & Commissioning Team | 50
6.4 | Installation Quality Audit | 10 | 2027-01-26 | 2027-02-04 | QA/QC Engineer | 40
6.5 | Fiber Continuity Test | 4 | 2027-01-31 | 2027-02-03 | Site Engineer | 0
6.6 | OTDR Baseline Test | 4 | 2027-02-02 | 2027-02-05 | QA/QC Engineer | 35
6.7 | End-to-End Fiber Test | 10 | 2027-02-04 | 2027-02-13 | Planning Engineer | 20
6.8 | Cable Attenuation Test | 6 | 2027-02-09 | 2027-02-14 | Commercial Team | 60
6.9 | Power System Testing | 6 | 2027-02-12 | 2027-02-17 | Procurement Engineer | 80
6.10 | Protection System Testing | 6 | 2027-02-15 | 2027-02-20 | HSE Officer | 25
6.11 | UPS Functional Test | 6 | 2027-02-18 | 2027-02-23 | QA/QC Engineer | 75
6.12 | Battery Performance Test | 4 | 2027-02-21 | 2027-02-24 | Commercial Team | 0
6.13 | Network Equipment Configuration | 6 | 2027-02-23 | 2027-02-28 | Fiber Installation Team | 0
6.14 | Network Connectivity Test | 4 | 2027-02-26 | 2027-03-01 | Testing & Commissioning Team | 0
6.15 | Alarm Verification | 2 | 2027-02-28 | 2027-03-01 | Site Engineer | 90
6.16 | SCADA/Monitoring Integration | 4 | 2027-03-01 | 2027-03-04 | Testing & Commissioning Team | 75
6.17 | Integrated System Testing | 2 | 2027-03-03 | 2027-03-04 | Site Engineer | 60
6.18 | Performance Test | 6 | 2027-03-04 | 2027-03-09 | Subcontractor Team | 70
6.19 | Reliability Run | 3 | 2027-03-07 | 2027-03-09 | Site Engineer | 25
6.20 | Test Report Compilation | 4 | 2027-03-08 | 2027-03-11 | Civil Engineer | 25
7 | HSE & Quality Management | 42 | 2027-03-10 | 2027-04-20 | Project Management Team | 44
7.1 | Project HSE Plan | 3 | 2027-03-10 | 2027-03-12 | Fiber Installation Team | 0
7.2 | Risk Assessment | 4 | 2027-03-11 | 2027-03-14 | Project Manager | 40
7.3 | Method Statement Approval | 2 | 2027-03-13 | 2027-03-14 | Procurement Engineer | 0
7.4 | Toolbox Talks | 2 | 2027-03-14 | 2027-03-15 | Planning Engineer | 25
7.5 | Daily Safety Inspection | 2 | 2027-03-15 | 2027-03-16 | QA/QC Engineer | 75
7.6 | Weekly HSE Audit | 6 | 2027-03-16 | 2027-03-21 | Site Engineer | 100
7.7 | Permit to Work Management | 7 | 2027-03-19 | 2027-03-25 | Electrical Engineer | 90
7.8 | Environmental Monitoring | 2 | 2027-03-22 | 2027-03-23 | Site Engineer | 40
7.9 | Waste Management | 5 | 2027-03-23 | 2027-03-27 | Electrical Engineer | 70
7.10 | Emergency Preparedness Drill | 8 | 2027-03-25 | 2027-04-01 | Planning Engineer | 75
7.11 | Quality Plan | 7 | 2027-03-29 | 2027-04-04 | QA/QC Engineer | 100
7.12 | Inspection Request Management | 4 | 2027-04-01 | 2027-04-04 | Civil Engineer | 40
7.13 | Material Test Certificate Review | 4 | 2027-04-03 | 2027-04-06 | Document Controller | 0
7.14 | NCR Management | 8 | 2027-04-05 | 2027-04-12 | Civil Engineer | 0
7.15 | Corrective Action Tracking | 7 | 2027-04-09 | 2027-04-15 | Document Controller | 25
7.16 | Quality Audit | 2 | 2027-04-12 | 2027-04-13 | Commercial Team | 25
7.17 | Final Quality Dossier | 8 | 2027-04-13 | 2027-04-20 | HSE Officer | 35
8 | Documentation & Handover | 63 | 2027-04-17 | 2027-06-18 | Project Management Team | 40
8.1 | Document Index Preparation | 2 | 2027-04-17 | 2027-04-18 | Site Engineer | 60
8.2 | Drawing Register | 5 | 2027-04-18 | 2027-04-22 | Project Manager | 60
8.3 | Approved for Construction Drawings | 16 | 2027-04-20 | 2027-05-05 | Design Engineer | 0
8.4 | As-Built Drawings | 3 | 2027-04-28 | 2027-04-30 | Project Manager | 0
8.5 | Cable Schedule | 4 | 2027-04-29 | 2027-05-02 | Site Engineer | 60
8.6 | Equipment Schedule | 6 | 2027-05-01 | 2027-05-06 | Fiber Installation Team | 0
8.7 | Test Certificates | 4 | 2027-05-04 | 2027-05-07 | Fiber Installation Team | 35
8.8 | Inspection Records | 5 | 2027-05-06 | 2027-05-10 | Procurement Engineer | 40
8.9 | Material Reconciliation | 8 | 2027-05-08 | 2027-05-15 | Procurement Engineer | 75
8.10 | Warranty Documents | 4 | 2027-05-12 | 2027-05-15 | QA/QC Engineer | 10
8.11 | O&M Manual | 2 | 2027-05-14 | 2027-05-15 | Document Controller | 75
8.12 | Spare Parts List | 10 | 2027-05-15 | 2027-05-24 | QA/QC Engineer | 75
8.13 | Training Material | 8 | 2027-05-20 | 2027-05-27 | Commercial Team | 25
8.14 | Operator Training | 4 | 2027-05-24 | 2027-05-27 | Project Manager | 20
8.15 | Maintenance Training | 2 | 2027-05-26 | 2027-05-27 | QA/QC Engineer | 25
8.16 | Client Walkdown | 9 | 2027-05-27 | 2027-06-04 | Civil Engineer | 40
8.17 | Punch List Preparation | 7 | 2027-05-31 | 2027-06-06 | Testing & Commissioning Team | 10
8.18 | Punch List Closure | 3 | 2027-06-03 | 2027-06-05 | Design Engineer | 100
8.19 | Final Handover Dossier | 10 | 2027-06-04 | 2027-06-13 | Testing & Commissioning Team | 0
8.20 | Taking Over Certificate | 10 | 2027-06-09 | 2027-06-18 | Civil Engineer | 100
9 | Project Closure | 52 | 2027-06-14 | 2027-08-04 | Project Management Team | 53
9.1 | Final Quantity Reconciliation | 7 | 2027-06-14 | 2027-06-20 | QA/QC Engineer | 75
9.2 | Final Measurement | 7 | 2027-06-17 | 2027-06-23 | Testing & Commissioning Team | 0
9.3 | Final Invoice Preparation | 2 | 2027-06-20 | 2027-06-21 | Procurement Engineer | 75
9.4 | Commercial Closure | 9 | 2027-06-21 | 2027-06-29 | Procurement Engineer | 0
9.5 | Subcontractor Closure | 10 | 2027-06-25 | 2027-07-04 | Design Engineer | 100
9.6 | Vendor Closure | 8 | 2027-06-30 | 2027-07-07 | Site Engineer | 80
9.7 | Site Demobilization | 5 | 2027-07-04 | 2027-07-08 | Subcontractor Team | 60
9.8 | Temporary Facility Removal | 6 | 2027-07-06 | 2027-07-11 | Subcontractor Team | 35
9.9 | Excess Material Return | 5 | 2027-07-09 | 2027-07-13 | Site Engineer | 35
9.10 | Lessons Learned Workshop | 9 | 2027-07-11 | 2027-07-19 | Electrical Engineer | 75
9.11 | Project Performance Review | 6 | 2027-07-15 | 2027-07-20 | Electrical Engineer | 90
9.12 | Final Cost Report | 6 | 2027-07-18 | 2027-07-23 | Design Engineer | 20
9.13 | Final Schedule Report | 8 | 2027-07-21 | 2027-07-28 | Electrical Engineer | 10
9.14 | Management Review | 2 | 2027-07-25 | 2027-07-26 | Subcontractor Team | 35
9.15 | Project Closure Report | 10 | 2027-07-26 | 2027-08-04 | Fiber Installation Team | 80
9.16 | Archive Project Records | 2 | 2027-07-31 | 2027-08-01 | Design Engineer | 75

## Instructions
Vindhya Telelinks Ltd. – Project WBS Practice Dataset
Purpose | Practice WBS, scheduling, resource allocation and % completion analysis in MS Excel / MS Project.
Records | 190 WBS rows including phase summary tasks.
Project Type | Telecom / EPC project – engineering, procurement, civil works, cable installation, testing and handover.
Columns | WBS, Task Name, Duration, Start Date, Finish Date, Resource Name, % Complete
Suggested Exercises | Create Gantt Chart, identify delayed tasks, resource-wise workload, phase-wise completion and project progress dashboard.
FS Gantt created
See 'FS Gantt' for the Finish-to-Start linked schedule and 'FS Summary' for management comparison.

## FS Gantt
Vindhya Telelinks Ltd. — Finish-to-Start (FS) Executive Gantt
Logic: each detailed activity starts 1 day after its predecessor finishes. Original WBS remains unchanged in the source sheets.
WBS | Task Name | Duration | Resource Name | % Complete | Predecessor | Link | FS Start | FS Finish | Baseline Start | Baseline Finish | Variance (days) | time axis 2026-01-05 to 2029-04-30
1.1 | Project Kick-off | 3 | QA/QC Engineer | 35% |  |  | 2026-01-05 | 2026-01-07 | 2026-01-05 | 2026-01-07 | 0 | bar: 2026-01-05
1.2 | Contract Review | 6 | Subcontractor Team | 75% | 1.1 | FS | 2026-01-08 | 2026-01-13 | 2026-01-06 | 2026-01-11 | 2 | bar: 2026-01-05 to 2026-01-12
1.3 | Scope Confirmation | 3 | HSE Officer | 20% | 1.2 | FS | 2026-01-14 | 2026-01-16 | 2026-01-09 | 2026-01-11 | 5 | bar: 2026-01-12
1.4 | Project Execution Plan | 10 | Commercial Team | 40% | 1.3 | FS | 2026-01-17 | 2026-01-26 | 2026-01-10 | 2026-01-19 | 7 | bar: 2026-01-12 to 2026-01-26
1.5 | Site Survey | 6 | Subcontractor Team | 60% | 1.4 | FS | 2026-01-27 | 2026-02-01 | 2026-01-15 | 2026-01-20 | 12 | bar: 2026-01-26
1.6 | Topographical Survey | 7 | Commercial Team | 90% | 1.5 | FS | 2026-02-02 | 2026-02-08 | 2026-01-18 | 2026-01-24 | 15 | bar: 2026-02-02
1.7 | Route Survey | 5 | Commercial Team | 90% | 1.6 | FS | 2026-02-09 | 2026-02-13 | 2026-01-21 | 2026-01-25 | 19 | bar: 2026-02-09
1.8 | Utility Survey | 6 | Procurement Engineer | 50% | 1.7 | FS | 2026-02-14 | 2026-02-19 | 2026-01-23 | 2026-01-28 | 22 | bar: 2026-02-09 to 2026-02-16
1.9 | Geotechnical Investigation | 2 | Planning Engineer | 70% | 1.8 | FS | 2026-02-20 | 2026-02-21 | 2026-01-26 | 2026-01-27 | 25 | bar: 2026-02-16
1.1 | Design Basis | 3 | Subcontractor Team | 25% | 1.9 | FS | 2026-02-22 | 2026-02-24 | 2026-01-27 | 2026-01-29 | 26 | bar: 2026-02-16 to 2026-02-23
1.11 | Basic Engineering | 3 | Project Manager | 50% | 1.1 | FS | 2026-02-25 | 2026-02-27 | 2026-01-28 | 2026-01-30 | 28 | bar: 2026-02-23
1.12 | Detailed Engineering | 9 | Site Engineer | 75% | 1.11 | FS | 2026-02-28 | 2026-03-08 | 2026-01-29 | 2026-02-06 | 30 | bar: 2026-02-23 to 2026-03-02
1.13 | Design Review | 3 | Civil Engineer | 40% | 1.12 | FS | 2026-03-09 | 2026-03-11 | 2026-02-02 | 2026-02-04 | 35 | bar: 2026-03-09
1.14 | Client Approval | 7 | Commercial Team | 35% | 1.13 | FS | 2026-03-12 | 2026-03-18 | 2026-02-03 | 2026-02-09 | 37 | bar: 2026-03-09 to 2026-03-16
1.15 | Engineering Change Management | 8 | QA/QC Engineer | 80% | 1.14 | FS | 2026-03-19 | 2026-03-26 | 2026-02-06 | 2026-02-13 | 41 | bar: 2026-03-16 to 2026-03-23
1.16 | Document Control | 3 | Site Engineer | 80% | 1.15 | FS | 2026-03-27 | 2026-03-29 | 2026-02-10 | 2026-02-12 | 45 | bar: 2026-03-23
2.1 | Procurement Plan | 6 | QA/QC Engineer | 60% | 1.16 | FS | 2026-03-30 | 2026-04-04 | 2026-02-11 | 2026-02-16 | 47 | bar: 2026-03-30
2.2 | Vendor Prequalification | 6 | Electrical Engineer | 25% | 2.1 | FS | 2026-04-05 | 2026-04-10 | 2026-02-14 | 2026-02-19 | 50 | bar: 2026-03-30 to 2026-04-06
2.3 | RFQ Preparation | 4 | Document Controller | 75% | 2.2 | FS | 2026-04-11 | 2026-04-14 | 2026-02-17 | 2026-02-20 | 53 | bar: 2026-04-06 to 2026-04-13
2.4 | RFQ Issue | 6 | Subcontractor Team | 0% | 2.3 | FS | 2026-04-15 | 2026-04-20 | 2026-02-19 | 2026-02-24 | 55 | bar: 2026-04-13 to 2026-04-20
2.5 | Technical Bid Evaluation | 7 | Electrical Engineer | 35% | 2.4 | FS | 2026-04-21 | 2026-04-27 | 2026-02-22 | 2026-02-28 | 58 | bar: 2026-04-20 to 2026-04-27
2.6 | Commercial Bid Evaluation | 8 | Fiber Installation Team | 0% | 2.5 | FS | 2026-04-28 | 2026-05-05 | 2026-02-25 | 2026-03-04 | 62 | bar: 2026-04-27 to 2026-05-04
2.7 | Vendor Finalization | 10 | Subcontractor Team | 50% | 2.6 | FS | 2026-05-06 | 2026-05-15 | 2026-03-01 | 2026-03-10 | 66 | bar: 2026-05-04 to 2026-05-11
2.8 | Purchase Order Release | 3 | QA/QC Engineer | 40% | 2.7 | FS | 2026-05-16 | 2026-05-18 | 2026-03-06 | 2026-03-08 | 71 | bar: 2026-05-11 to 2026-05-18
2.9 | Cable Raw Material Procurement | 17 | Subcontractor Team | 90% | 2.8 | FS | 2026-05-19 | 2026-06-04 | 2026-03-07 | 2026-03-23 | 73 | bar: 2026-05-18 to 2026-06-01
2.1 | Optical Fiber Procurement | 14 | Fiber Installation Team | 50% | 2.9 | FS | 2026-06-05 | 2026-06-18 | 2026-03-15 | 2026-03-28 | 82 | bar: 2026-06-01 to 2026-06-15
2.11 | HDPE Duct Procurement | 13 | Subcontractor Team | 25% | 2.1 | FS | 2026-06-19 | 2026-07-01 | 2026-03-22 | 2026-04-03 | 89 | bar: 2026-06-15 to 2026-06-29
2.12 | Joint Closure Procurement | 11 | Electrical Engineer | 70% | 2.11 | FS | 2026-07-02 | 2026-07-12 | 2026-03-28 | 2026-04-07 | 96 | bar: 2026-06-29 to 2026-07-06
2.13 | Fiber Accessories Procurement | 13 | Commercial Team | 60% | 2.12 | FS | 2026-07-13 | 2026-07-25 | 2026-04-02 | 2026-04-14 | 102 | bar: 2026-07-13 to 2026-07-20
2.14 | Electrical Materials Procurement | 5 | Procurement Engineer | 70% | 2.13 | FS | 2026-07-26 | 2026-07-30 | 2026-04-08 | 2026-04-12 | 109 | bar: 2026-07-20 to 2026-07-27
2.15 | Earthing Materials Procurement | 17 | Subcontractor Team | 10% | 2.14 | FS | 2026-07-31 | 2026-08-16 | 2026-04-10 | 2026-04-26 | 112 | bar: 2026-07-27 to 2026-08-10
2.16 | PPE Procurement | 5 | QA/QC Engineer | 80% | 2.15 | FS | 2026-08-17 | 2026-08-21 | 2026-04-18 | 2026-04-22 | 121 | bar: 2026-08-17
2.17 | Inspection & Test Plan | 2 | HSE Officer | 80% | 2.16 | FS | 2026-08-22 | 2026-08-23 | 2026-04-20 | 2026-04-21 | 124 | bar: 2026-08-17
2.18 | Vendor Inspection | 5 | Design Engineer | 50% | 2.17 | FS | 2026-08-24 | 2026-08-28 | 2026-04-21 | 2026-04-25 | 125 | bar: 2026-08-24
2.19 | Factory Acceptance Test | 9 | Subcontractor Team | 20% | 2.18 | FS | 2026-08-29 | 2026-09-06 | 2026-04-23 | 2026-05-01 | 128 | bar: 2026-08-24 to 2026-08-31
2.2 | Material Dispatch | 3 | Document Controller | 75% | 2.19 | FS | 2026-09-07 | 2026-09-09 | 2026-04-27 | 2026-04-29 | 133 | bar: 2026-09-07
2.21 | Material Receipt | 9 | Electrical Engineer | 75% | 2.2 | FS | 2026-09-10 | 2026-09-18 | 2026-04-28 | 2026-05-06 | 135 | bar: 2026-09-07 to 2026-09-14
2.22 | Material Inspection | 6 | QA/QC Engineer | 25% | 2.21 | FS | 2026-09-19 | 2026-09-24 | 2026-05-02 | 2026-05-07 | 140 | bar: 2026-09-14 to 2026-09-21
2.23 | Material Storage | 8 | Civil Engineer | 75% | 2.22 | FS | 2026-09-25 | 2026-10-02 | 2026-05-05 | 2026-05-12 | 143 | bar: 2026-09-21 to 2026-09-28
3.1 | Site Mobilization | 10 | Testing & Commissioning Team | 90% | 2.23 | FS | 2026-10-03 | 2026-10-12 | 2026-05-09 | 2026-05-18 | 147 | bar: 2026-09-28 to 2026-10-12
3.2 | Site Office Setup | 10 | Electrical Engineer | 80% | 3.1 | FS | 2026-10-13 | 2026-10-22 | 2026-05-14 | 2026-05-23 | 152 | bar: 2026-10-12 to 2026-10-19
3.3 | Temporary Power Arrangement | 8 | Procurement Engineer | 40% | 3.2 | FS | 2026-10-23 | 2026-10-30 | 2026-05-19 | 2026-05-26 | 157 | bar: 2026-10-19 to 2026-10-26
3.4 | Temporary Water Arrangement | 6 | Civil Engineer | 100% | 3.3 | FS | 2026-10-31 | 2026-11-05 | 2026-05-23 | 2026-05-28 | 161 | bar: 2026-10-26 to 2026-11-02
3.5 | Site Barricading | 2 | Design Engineer | 0% | 3.4 | FS | 2026-11-06 | 2026-11-07 | 2026-05-26 | 2026-05-27 | 164 | bar: 2026-11-02
3.6 | Safety Signage | 9 | QA/QC Engineer | 90% | 3.5 | FS | 2026-11-08 | 2026-11-16 | 2026-05-27 | 2026-06-04 | 165 | bar: 2026-11-02 to 2026-11-16
3.7 | Access Road Preparation | 9 | Procurement Engineer | 35% | 3.6 | FS | 2026-11-17 | 2026-11-25 | 2026-05-31 | 2026-06-08 | 170 | bar: 2026-11-16 to 2026-11-23
3.8 | Survey Benchmark Establishment | 4 | Electrical Engineer | 80% | 3.7 | FS | 2026-11-26 | 2026-11-29 | 2026-06-04 | 2026-06-07 | 175 | bar: 2026-11-23
3.9 | Excavation Marking | 9 | Commercial Team | 60% | 3.8 | FS | 2026-11-30 | 2026-12-08 | 2026-06-06 | 2026-06-14 | 177 | bar: 2026-11-30 to 2026-12-07
3.1 | Trench Excavation | 9 | Fiber Installation Team | 90% | 3.9 | FS | 2026-12-09 | 2026-12-17 | 2026-06-10 | 2026-06-18 | 182 | bar: 2026-12-07 to 2026-12-14
3.11 | Road Crossing Preparation | 10 | Project Manager | 75% | 3.1 | FS | 2026-12-18 | 2026-12-27 | 2026-06-14 | 2026-06-23 | 187 | bar: 2026-12-14 to 2026-12-21
3.12 | Duct Bank Excavation | 6 | Electrical Engineer | 35% | 3.11 | FS | 2026-12-28 | 2027-01-02 | 2026-06-19 | 2026-06-24 | 192 | bar: 2026-12-28
3.13 | Sand Bedding | 3 | Document Controller | 50% | 3.12 | FS | 2027-01-03 | 2027-01-05 | 2026-06-22 | 2026-06-24 | 195 | bar: 2026-12-28 to 2027-01-04
3.14 | Duct Installation | 16 | QA/QC Engineer | 90% | 3.13 | FS | 2027-01-06 | 2027-01-21 | 2026-06-23 | 2026-07-08 | 197 | bar: 2027-01-04 to 2027-01-18
3.15 | Duct Jointing | 6 | Design Engineer | 50% | 3.14 | FS | 2027-01-22 | 2027-01-27 | 2026-07-01 | 2026-07-06 | 205 | bar: 2027-01-18 to 2027-01-25
3.16 | Warning Tape Installation | 11 | Document Controller | 100% | 3.15 | FS | 2027-01-28 | 2027-02-07 | 2026-07-04 | 2026-07-14 | 208 | bar: 2027-01-25 to 2027-02-01
3.17 | Backfilling | 9 | Testing & Commissioning Team | 0% | 3.16 | FS | 2027-02-08 | 2027-02-16 | 2026-07-09 | 2026-07-17 | 214 | bar: 2027-02-08 to 2027-02-15
3.18 | Compaction | 6 | Site Engineer | 50% | 3.17 | FS | 2027-02-17 | 2027-02-22 | 2026-07-13 | 2026-07-18 | 219 | bar: 2027-02-15 to 2027-02-22
3.19 | Manhole Construction | 6 | Document Controller | 20% | 3.18 | FS | 2027-02-23 | 2027-02-28 | 2026-07-16 | 2026-07-21 | 222 | bar: 2027-02-22
3.2 | Handhole Construction | 18 | Design Engineer | 40% | 3.19 | FS | 2027-03-01 | 2027-03-18 | 2026-07-19 | 2026-08-05 | 225 | bar: 2027-03-01 to 2027-03-15
3.21 | Foundation Works | 9 | Planning Engineer | 0% | 3.2 | FS | 2027-03-19 | 2027-03-27 | 2026-07-28 | 2026-08-05 | 234 | bar: 2027-03-15 to 2027-03-22
3.22 | Restoration of Road Surface | 2 | HSE Officer | 50% | 3.21 | FS | 2027-03-28 | 2027-03-29 | 2026-08-01 | 2026-08-02 | 239 | bar: 2027-03-22 to 2027-03-29
3.23 | Site Drainage | 10 | Planning Engineer | 100% | 3.22 | FS | 2027-03-30 | 2027-04-08 | 2026-08-02 | 2026-08-11 | 240 | bar: 2027-03-29 to 2027-04-05
3.24 | Civil Snag Rectification | 5 | Planning Engineer | 20% | 3.23 | FS | 2027-04-09 | 2027-04-13 | 2026-08-07 | 2026-08-11 | 245 | bar: 2027-04-05 to 2027-04-12
4.1 | Cable Drum Inspection | 6 | Commercial Team | 0% | 3.24 | FS | 2027-04-14 | 2027-04-19 | 2026-08-09 | 2026-08-14 | 248 | bar: 2027-04-12 to 2027-04-19
4.2 | Cable Drum Handling | 10 | Testing & Commissioning Team | 25% | 4.1 | FS | 2027-04-20 | 2027-04-29 | 2026-08-12 | 2026-08-21 | 251 | bar: 2027-04-19 to 2027-04-26
4.3 | Cable Route Preparation | 7 | Project Manager | 10% | 4.2 | FS | 2027-04-30 | 2027-05-06 | 2026-08-17 | 2026-08-23 | 256 | bar: 2027-04-26 to 2027-05-03
4.4 | Cable Pulling Plan | 7 | HSE Officer | 75% | 4.3 | FS | 2027-05-07 | 2027-05-13 | 2026-08-20 | 2026-08-26 | 260 | bar: 2027-05-03 to 2027-05-10
4.5 | Optical Fiber Cable Pulling | 9 | Document Controller | 80% | 4.4 | FS | 2027-05-14 | 2027-05-22 | 2026-08-23 | 2026-08-31 | 264 | bar: 2027-05-10 to 2027-05-17
4.6 | Power Cable Pulling | 4 | Procurement Engineer | 60% | 4.5 | FS | 2027-05-23 | 2027-05-26 | 2026-08-27 | 2026-08-30 | 269 | bar: 2027-05-17 to 2027-05-24
4.7 | Control Cable Pulling | 9 | Design Engineer | 70% | 4.6 | FS | 2027-05-27 | 2027-06-04 | 2026-08-29 | 2026-09-06 | 271 | bar: 2027-05-24 to 2027-05-31
4.8 | Cable Blowing | 10 | Planning Engineer | 25% | 4.7 | FS | 2027-06-05 | 2027-06-14 | 2026-09-02 | 2026-09-11 | 276 | bar: 2027-05-31 to 2027-06-14
4.9 | Cable Dressing | 8 | Design Engineer | 75% | 4.8 | FS | 2027-06-15 | 2027-06-22 | 2026-09-07 | 2026-09-14 | 281 | bar: 2027-06-14 to 2027-06-21
4.1 | Cable Identification | 4 | Commercial Team | 90% | 4.9 | FS | 2027-06-23 | 2027-06-26 | 2026-09-11 | 2026-09-14 | 285 | bar: 2027-06-21
4.11 | Cable Tagging | 6 | Fiber Installation Team | 60% | 4.1 | FS | 2027-06-27 | 2027-07-02 | 2026-09-13 | 2026-09-18 | 287 | bar: 2027-06-21 to 2027-06-28
4.12 | Joint Pit Preparation | 8 | Design Engineer | 90% | 4.11 | FS | 2027-07-03 | 2027-07-10 | 2026-09-16 | 2026-09-23 | 290 | bar: 2027-06-28 to 2027-07-05
4.13 | Joint Closure Installation | 13 | Procurement Engineer | 90% | 4.12 | FS | 2027-07-11 | 2027-07-23 | 2026-09-20 | 2026-10-02 | 294 | bar: 2027-07-05 to 2027-07-19
4.14 | Fiber Splicing | 8 | Planning Engineer | 0% | 4.13 | FS | 2027-07-24 | 2027-07-31 | 2026-09-26 | 2026-10-03 | 301 | bar: 2027-07-19 to 2027-07-26
4.15 | Splice Tray Installation | 11 | Project Manager | 0% | 4.14 | FS | 2027-08-01 | 2027-08-11 | 2026-09-30 | 2026-10-10 | 305 | bar: 2027-07-26 to 2027-08-09
4.16 | OTDR Testing | 4 | Site Engineer | 75% | 4.15 | FS | 2027-08-12 | 2027-08-15 | 2026-10-05 | 2026-10-08 | 311 | bar: 2027-08-09
4.17 | Power Meter Testing | 2 | QA/QC Engineer | 0% | 4.16 | FS | 2027-08-16 | 2027-08-17 | 2026-10-07 | 2026-10-08 | 313 | bar: 2027-08-16
4.18 | Link Loss Testing | 5 | Testing & Commissioning Team | 35% | 4.17 | FS | 2027-08-18 | 2027-08-22 | 2026-10-08 | 2026-10-12 | 314 | bar: 2027-08-16
4.19 | Cable Termination | 6 | Site Engineer | 50% | 4.18 | FS | 2027-08-23 | 2027-08-28 | 2026-10-10 | 2026-10-15 | 317 | bar: 2027-08-23
4.2 | ODF Installation | 6 | Electrical Engineer | 50% | 4.19 | FS | 2027-08-29 | 2027-09-03 | 2026-10-13 | 2026-10-18 | 320 | bar: 2027-08-23 to 2027-08-30
4.21 | Patch Panel Installation | 14 | Commercial Team | 70% | 4.2 | FS | 2027-09-04 | 2027-09-17 | 2026-10-16 | 2026-10-29 | 323 | bar: 2027-08-30 to 2027-09-13
4.22 | Rack Installation | 7 | HSE Officer | 10% | 4.21 | FS | 2027-09-18 | 2027-09-24 | 2026-10-23 | 2026-10-29 | 330 | bar: 2027-09-13 to 2027-09-20
4.23 | Network Equipment Installation | 13 | Fiber Installation Team | 20% | 4.22 | FS | 2027-09-25 | 2027-10-07 | 2026-10-26 | 2026-11-07 | 334 | bar: 2027-09-20 to 2027-10-04
4.24 | Equipment Earthing | 7 | HSE Officer | 50% | 4.23 | FS | 2027-10-08 | 2027-10-14 | 2026-11-01 | 2026-11-07 | 341 | bar: 2027-10-04 to 2027-10-11
4.25 | Cable Management | 5 | Document Controller | 75% | 4.24 | FS | 2027-10-15 | 2027-10-19 | 2026-11-04 | 2026-11-08 | 345 | bar: 2027-10-11 to 2027-10-18
4.26 | Labeling & Identification | 3 | Fiber Installation Team | 60% | 4.25 | FS | 2027-10-20 | 2027-10-22 | 2026-11-06 | 2026-11-08 | 348 | bar: 2027-10-18
4.27 | As-Built Route Verification | 2 | Testing & Commissioning Team | 20% | 4.26 | FS | 2027-10-23 | 2027-10-24 | 2026-11-07 | 2026-11-08 | 350 | bar: 2027-10-18
5.1 | Electrical Load Assessment | 3 | Testing & Commissioning Team | 0% | 4.27 | FS | 2027-10-25 | 2027-10-27 | 2026-11-08 | 2026-11-10 | 351 | bar: 2027-10-25
5.2 | LT Panel Installation | 13 | Project Manager | 100% | 5.1 | FS | 2027-10-28 | 2027-11-09 | 2026-11-09 | 2026-11-21 | 353 | bar: 2027-10-25 to 2027-11-08
5.3 | Distribution Board Installation | 12 | Commercial Team | 100% | 5.2 | FS | 2027-11-10 | 2027-11-21 | 2026-11-15 | 2026-11-26 | 360 | bar: 2027-11-08 to 2027-11-15
5.4 | UPS Installation | 15 | Electrical Engineer | 20% | 5.3 | FS | 2027-11-22 | 2027-12-06 | 2026-11-21 | 2026-12-05 | 366 | bar: 2027-11-22 to 2027-12-06
5.5 | Battery Bank Installation | 16 | Project Manager | 75% | 5.4 | FS | 2027-12-07 | 2027-12-22 | 2026-11-28 | 2026-12-13 | 374 | bar: 2027-12-06 to 2027-12-20
5.6 | Lighting Installation | 7 | QA/QC Engineer | 75% | 5.5 | FS | 2027-12-23 | 2027-12-29 | 2026-12-06 | 2026-12-12 | 382 | bar: 2027-12-20 to 2027-12-27
5.7 | Small Power Installation | 8 | QA/QC Engineer | 90% | 5.6 | FS | 2027-12-30 | 2028-01-06 | 2026-12-09 | 2026-12-16 | 386 | bar: 2027-12-27 to 2028-01-03
5.8 | Earthing Grid Installation | 7 | Testing & Commissioning Team | 10% | 5.7 | FS | 2028-01-07 | 2028-01-13 | 2026-12-13 | 2026-12-19 | 390 | bar: 2028-01-03 to 2028-01-10
5.9 | Equipment Earthing | 4 | Civil Engineer | 40% | 5.8 | FS | 2028-01-14 | 2028-01-17 | 2026-12-16 | 2026-12-19 | 394 | bar: 2028-01-10 to 2028-01-17
5.1 | Lightning Protection | 8 | Fiber Installation Team | 60% | 5.9 | FS | 2028-01-18 | 2028-01-25 | 2026-12-18 | 2026-12-25 | 396 | bar: 2028-01-17 to 2028-01-24
5.11 | Cable Tray Installation | 18 | Fiber Installation Team | 0% | 5.1 | FS | 2028-01-26 | 2028-02-12 | 2026-12-22 | 2027-01-08 | 400 | bar: 2028-01-24 to 2028-02-07
5.12 | Cable Tray Earthing | 6 | Site Engineer | 10% | 5.11 | FS | 2028-02-13 | 2028-02-18 | 2026-12-31 | 2027-01-05 | 409 | bar: 2028-02-07 to 2028-02-14
5.13 | Control Panel Installation | 7 | Electrical Engineer | 25% | 5.12 | FS | 2028-02-19 | 2028-02-25 | 2027-01-03 | 2027-01-09 | 412 | bar: 2028-02-14 to 2028-02-21
5.14 | Auxiliary Cable Termination | 9 | Subcontractor Team | 90% | 5.13 | FS | 2028-02-26 | 2028-03-05 | 2027-01-06 | 2027-01-14 | 416 | bar: 2028-02-21 to 2028-02-28
5.15 | Electrical Continuity Test | 8 | Electrical Engineer | 25% | 5.14 | FS | 2028-03-06 | 2028-03-13 | 2027-01-10 | 2027-01-17 | 421 | bar: 2028-03-06 to 2028-03-13
5.16 | Insulation Resistance Test | 4 | QA/QC Engineer | 35% | 5.15 | FS | 2028-03-14 | 2028-03-17 | 2027-01-14 | 2027-01-17 | 425 | bar: 2028-03-13
5.17 | Functional Testing | 5 | Planning Engineer | 50% | 5.16 | FS | 2028-03-18 | 2028-03-22 | 2027-01-16 | 2027-01-20 | 427 | bar: 2028-03-13 to 2028-03-20
5.18 | Electrical Safety Inspection | 6 | QA/QC Engineer | 90% | 5.17 | FS | 2028-03-23 | 2028-03-28 | 2027-01-18 | 2027-01-23 | 430 | bar: 2028-03-20 to 2028-03-27
6.1 | Commissioning Plan | 6 | Planning Engineer | 100% | 5.18 | FS | 2028-03-29 | 2028-04-03 | 2027-01-21 | 2027-01-26 | 433 | bar: 2028-03-27 to 2028-04-03
6.2 | Pre-Commissioning Inspection | 3 | Project Manager | 20% | 6.1 | FS | 2028-04-04 | 2028-04-06 | 2027-01-24 | 2027-01-26 | 436 | bar: 2028-04-03
6.3 | Mechanical Completion | 3 | Testing & Commissioning Team | 50% | 6.2 | FS | 2028-04-07 | 2028-04-09 | 2027-01-25 | 2027-01-27 | 438 | bar: 2028-04-03
6.4 | Installation Quality Audit | 10 | QA/QC Engineer | 40% | 6.3 | FS | 2028-04-10 | 2028-04-19 | 2027-01-26 | 2027-02-04 | 440 | bar: 2028-04-10 to 2028-04-17
6.5 | Fiber Continuity Test | 4 | Site Engineer | 0% | 6.4 | FS | 2028-04-20 | 2028-04-23 | 2027-01-31 | 2027-02-03 | 445 | bar: 2028-04-17
6.6 | OTDR Baseline Test | 4 | QA/QC Engineer | 35% | 6.5 | FS | 2028-04-24 | 2028-04-27 | 2027-02-02 | 2027-02-05 | 447 | bar: 2028-04-24
6.7 | End-to-End Fiber Test | 10 | Planning Engineer | 20% | 6.6 | FS | 2028-04-28 | 2028-05-07 | 2027-02-04 | 2027-02-13 | 449 | bar: 2028-04-24 to 2028-05-01
6.8 | Cable Attenuation Test | 6 | Commercial Team | 60% | 6.7 | FS | 2028-05-08 | 2028-05-13 | 2027-02-09 | 2027-02-14 | 454 | bar: 2028-05-08
6.9 | Power System Testing | 6 | Procurement Engineer | 80% | 6.8 | FS | 2028-05-14 | 2028-05-19 | 2027-02-12 | 2027-02-17 | 457 | bar: 2028-05-08 to 2028-05-15
6.1 | Protection System Testing | 6 | HSE Officer | 25% | 6.9 | FS | 2028-05-20 | 2028-05-25 | 2027-02-15 | 2027-02-20 | 460 | bar: 2028-05-15 to 2028-05-22
6.11 | UPS Functional Test | 6 | QA/QC Engineer | 75% | 6.1 | FS | 2028-05-26 | 2028-05-31 | 2027-02-18 | 2027-02-23 | 463 | bar: 2028-05-22 to 2028-05-29
6.12 | Battery Performance Test | 4 | Commercial Team | 0% | 6.11 | FS | 2028-06-01 | 2028-06-04 | 2027-02-21 | 2027-02-24 | 466 | bar: 2028-05-29
6.13 | Network Equipment Configuration | 6 | Fiber Installation Team | 0% | 6.12 | FS | 2028-06-05 | 2028-06-10 | 2027-02-23 | 2027-02-28 | 468 | bar: 2028-06-05
6.14 | Network Connectivity Test | 4 | Testing & Commissioning Team | 0% | 6.13 | FS | 2028-06-11 | 2028-06-14 | 2027-02-26 | 2027-03-01 | 471 | bar: 2028-06-05 to 2028-06-12
6.15 | Alarm Verification | 2 | Site Engineer | 90% | 6.14 | FS | 2028-06-15 | 2028-06-16 | 2027-02-28 | 2027-03-01 | 473 | bar: 2028-06-12
6.16 | SCADA/Monitoring Integration | 4 | Testing & Commissioning Team | 75% | 6.15 | FS | 2028-06-17 | 2028-06-20 | 2027-03-01 | 2027-03-04 | 474 | bar: 2028-06-12 to 2028-06-19
6.17 | Integrated System Testing | 2 | Site Engineer | 60% | 6.16 | FS | 2028-06-21 | 2028-06-22 | 2027-03-03 | 2027-03-04 | 476 | bar: 2028-06-19
6.18 | Performance Test | 6 | Subcontractor Team | 70% | 6.17 | FS | 2028-06-23 | 2028-06-28 | 2027-03-04 | 2027-03-09 | 477 | bar: 2028-06-19 to 2028-06-26
6.19 | Reliability Run | 3 | Site Engineer | 25% | 6.18 | FS | 2028-06-29 | 2028-07-01 | 2027-03-07 | 2027-03-09 | 480 | bar: 2028-06-26
6.2 | Test Report Compilation | 4 | Civil Engineer | 25% | 6.19 | FS | 2028-07-02 | 2028-07-05 | 2027-03-08 | 2027-03-11 | 482 | bar: 2028-06-26 to 2028-07-03
7.1 | Project HSE Plan | 3 | Fiber Installation Team | 0% | 6.2 | FS | 2028-07-06 | 2028-07-08 | 2027-03-10 | 2027-03-12 | 484 | bar: 2028-07-03
7.2 | Risk Assessment | 4 | Project Manager | 40% | 7.1 | FS | 2028-07-09 | 2028-07-12 | 2027-03-11 | 2027-03-14 | 486 | bar: 2028-07-03 to 2028-07-10
7.3 | Method Statement Approval | 2 | Procurement Engineer | 0% | 7.2 | FS | 2028-07-13 | 2028-07-14 | 2027-03-13 | 2027-03-14 | 488 | bar: 2028-07-10
7.4 | Toolbox Talks | 2 | Planning Engineer | 25% | 7.3 | FS | 2028-07-15 | 2028-07-16 | 2027-03-14 | 2027-03-15 | 489 | bar: 2028-07-10
7.5 | Daily Safety Inspection | 2 | QA/QC Engineer | 75% | 7.4 | FS | 2028-07-17 | 2028-07-18 | 2027-03-15 | 2027-03-16 | 490 | bar: 2028-07-17
7.6 | Weekly HSE Audit | 6 | Site Engineer | 100% | 7.5 | FS | 2028-07-19 | 2028-07-24 | 2027-03-16 | 2027-03-21 | 491 | bar: 2028-07-17 to 2028-07-24
7.7 | Permit to Work Management | 7 | Electrical Engineer | 90% | 7.6 | FS | 2028-07-25 | 2028-07-31 | 2027-03-19 | 2027-03-25 | 494 | bar: 2028-07-24 to 2028-07-31
7.8 | Environmental Monitoring | 2 | Site Engineer | 40% | 7.7 | FS | 2028-08-01 | 2028-08-02 | 2027-03-22 | 2027-03-23 | 498 | bar: 2028-07-31
7.9 | Waste Management | 5 | Electrical Engineer | 70% | 7.8 | FS | 2028-08-03 | 2028-08-07 | 2027-03-23 | 2027-03-27 | 499 | bar: 2028-07-31 to 2028-08-07
7.1 | Emergency Preparedness Drill | 8 | Planning Engineer | 75% | 7.9 | FS | 2028-08-08 | 2028-08-15 | 2027-03-25 | 2027-04-01 | 502 | bar: 2028-08-07 to 2028-08-14
7.11 | Quality Plan | 7 | QA/QC Engineer | 100% | 7.1 | FS | 2028-08-16 | 2028-08-22 | 2027-03-29 | 2027-04-04 | 506 | bar: 2028-08-14 to 2028-08-21
7.12 | Inspection Request Management | 4 | Civil Engineer | 40% | 7.11 | FS | 2028-08-23 | 2028-08-26 | 2027-04-01 | 2027-04-04 | 510 | bar: 2028-08-21
7.13 | Material Test Certificate Review | 4 | Document Controller | 0% | 7.12 | FS | 2028-08-27 | 2028-08-30 | 2027-04-03 | 2027-04-06 | 512 | bar: 2028-08-21 to 2028-08-28
7.14 | NCR Management | 8 | Civil Engineer | 0% | 7.13 | FS | 2028-08-31 | 2028-09-07 | 2027-04-05 | 2027-04-12 | 514 | bar: 2028-08-28 to 2028-09-04
7.15 | Corrective Action Tracking | 7 | Document Controller | 25% | 7.14 | FS | 2028-09-08 | 2028-09-14 | 2027-04-09 | 2027-04-15 | 518 | bar: 2028-09-04 to 2028-09-11
7.16 | Quality Audit | 2 | Commercial Team | 25% | 7.15 | FS | 2028-09-15 | 2028-09-16 | 2027-04-12 | 2027-04-13 | 522 | bar: 2028-09-11
7.17 | Final Quality Dossier | 8 | HSE Officer | 35% | 7.16 | FS | 2028-09-17 | 2028-09-24 | 2027-04-13 | 2027-04-20 | 523 | bar: 2028-09-11 to 2028-09-18
8.1 | Document Index Preparation | 2 | Site Engineer | 60% | 7.17 | FS | 2028-09-25 | 2028-09-26 | 2027-04-17 | 2027-04-18 | 527 | bar: 2028-09-25
8.2 | Drawing Register | 5 | Project Manager | 60% | 8.1 | FS | 2028-09-27 | 2028-10-01 | 2027-04-18 | 2027-04-22 | 528 | bar: 2028-09-25
8.3 | Approved for Construction Drawings | 16 | Design Engineer | 0% | 8.2 | FS | 2028-10-02 | 2028-10-17 | 2027-04-20 | 2027-05-05 | 531 | bar: 2028-10-02 to 2028-10-16
8.4 | As-Built Drawings | 3 | Project Manager | 0% | 8.3 | FS | 2028-10-18 | 2028-10-20 | 2027-04-28 | 2027-04-30 | 539 | bar: 2028-10-16
8.5 | Cable Schedule | 4 | Site Engineer | 60% | 8.4 | FS | 2028-10-21 | 2028-10-24 | 2027-04-29 | 2027-05-02 | 541 | bar: 2028-10-16 to 2028-10-23
8.6 | Equipment Schedule | 6 | Fiber Installation Team | 0% | 8.5 | FS | 2028-10-25 | 2028-10-30 | 2027-05-01 | 2027-05-06 | 543 | bar: 2028-10-23 to 2028-10-30
8.7 | Test Certificates | 4 | Fiber Installation Team | 35% | 8.6 | FS | 2028-10-31 | 2028-11-03 | 2027-05-04 | 2027-05-07 | 546 | bar: 2028-10-30
8.8 | Inspection Records | 5 | Procurement Engineer | 40% | 8.7 | FS | 2028-11-04 | 2028-11-08 | 2027-05-06 | 2027-05-10 | 548 | bar: 2028-10-30 to 2028-11-06
8.9 | Material Reconciliation | 8 | Procurement Engineer | 75% | 8.8 | FS | 2028-11-09 | 2028-11-16 | 2027-05-08 | 2027-05-15 | 551 | bar: 2028-11-06 to 2028-11-13
8.1 | Warranty Documents | 4 | QA/QC Engineer | 10% | 8.9 | FS | 2028-11-17 | 2028-11-20 | 2027-05-12 | 2027-05-15 | 555 | bar: 2028-11-13 to 2028-11-20
8.11 | O&M Manual | 2 | Document Controller | 75% | 8.1 | FS | 2028-11-21 | 2028-11-22 | 2027-05-14 | 2027-05-15 | 557 | bar: 2028-11-20
8.12 | Spare Parts List | 10 | QA/QC Engineer | 75% | 8.11 | FS | 2028-11-23 | 2028-12-02 | 2027-05-15 | 2027-05-24 | 558 | bar: 2028-11-20 to 2028-11-27
8.13 | Training Material | 8 | Commercial Team | 25% | 8.12 | FS | 2028-12-03 | 2028-12-10 | 2027-05-20 | 2027-05-27 | 563 | bar: 2028-11-27 to 2028-12-04
8.14 | Operator Training | 4 | Project Manager | 20% | 8.13 | FS | 2028-12-11 | 2028-12-14 | 2027-05-24 | 2027-05-27 | 567 | bar: 2028-12-11
8.15 | Maintenance Training | 2 | QA/QC Engineer | 25% | 8.14 | FS | 2028-12-15 | 2028-12-16 | 2027-05-26 | 2027-05-27 | 569 | bar: 2028-12-11
8.16 | Client Walkdown | 9 | Civil Engineer | 40% | 8.15 | FS | 2028-12-17 | 2028-12-25 | 2027-05-27 | 2027-06-04 | 570 | bar: 2028-12-11 to 2028-12-25
8.17 | Punch List Preparation | 7 | Testing & Commissioning Team | 10% | 8.16 | FS | 2028-12-26 | 2029-01-01 | 2027-05-31 | 2027-06-06 | 575 | bar: 2028-12-25 to 2029-01-01
8.18 | Punch List Closure | 3 | Design Engineer | 100% | 8.17 | FS | 2029-01-02 | 2029-01-04 | 2027-06-03 | 2027-06-05 | 579 | bar: 2029-01-01
8.19 | Final Handover Dossier | 10 | Testing & Commissioning Team | 0% | 8.18 | FS | 2029-01-05 | 2029-01-14 | 2027-06-04 | 2027-06-13 | 581 | bar: 2029-01-01 to 2029-01-08
8.2 | Taking Over Certificate | 10 | Civil Engineer | 100% | 8.19 | FS | 2029-01-15 | 2029-01-24 | 2027-06-09 | 2027-06-18 | 586 | bar: 2029-01-15 to 2029-01-22
9.1 | Final Quantity Reconciliation | 7 | QA/QC Engineer | 75% | 8.2 | FS | 2029-01-25 | 2029-01-31 | 2027-06-14 | 2027-06-20 | 591 | bar: 2029-01-22 to 2029-01-29
9.2 | Final Measurement | 7 | Testing & Commissioning Team | 0% | 9.1 | FS | 2029-02-01 | 2029-02-07 | 2027-06-17 | 2027-06-23 | 595 | bar: 2029-01-29 to 2029-02-05
9.3 | Final Invoice Preparation | 2 | Procurement Engineer | 75% | 9.2 | FS | 2029-02-08 | 2029-02-09 | 2027-06-20 | 2027-06-21 | 599 | bar: 2029-02-05
9.4 | Commercial Closure | 9 | Procurement Engineer | 0% | 9.3 | FS | 2029-02-10 | 2029-02-18 | 2027-06-21 | 2027-06-29 | 600 | bar: 2029-02-05 to 2029-02-12
9.5 | Subcontractor Closure | 10 | Design Engineer | 100% | 9.4 | FS | 2029-02-19 | 2029-02-28 | 2027-06-25 | 2027-07-04 | 605 | bar: 2029-02-19 to 2029-02-26
9.6 | Vendor Closure | 8 | Site Engineer | 80% | 9.5 | FS | 2029-03-01 | 2029-03-08 | 2027-06-30 | 2027-07-07 | 610 | bar: 2029-02-26 to 2029-03-05
9.7 | Site Demobilization | 5 | Subcontractor Team | 60% | 9.6 | FS | 2029-03-09 | 2029-03-13 | 2027-07-04 | 2027-07-08 | 614 | bar: 2029-03-05 to 2029-03-12
9.8 | Temporary Facility Removal | 6 | Subcontractor Team | 35% | 9.7 | FS | 2029-03-14 | 2029-03-19 | 2027-07-06 | 2027-07-11 | 617 | bar: 2029-03-12 to 2029-03-19
9.9 | Excess Material Return | 5 | Site Engineer | 35% | 9.8 | FS | 2029-03-20 | 2029-03-24 | 2027-07-09 | 2027-07-13 | 620 | bar: 2029-03-19
9.1 | Lessons Learned Workshop | 9 | Electrical Engineer | 75% | 9.9 | FS | 2029-03-25 | 2029-04-02 | 2027-07-11 | 2027-07-19 | 623 | bar: 2029-03-19 to 2029-04-02
9.11 | Project Performance Review | 6 | Electrical Engineer | 90% | 9.1 | FS | 2029-04-03 | 2029-04-08 | 2027-07-15 | 2027-07-20 | 628 | bar: 2029-04-02
9.12 | Final Cost Report | 6 | Design Engineer | 20% | 9.11 | FS | 2029-04-09 | 2029-04-14 | 2027-07-18 | 2027-07-23 | 631 | bar: 2029-04-09
9.13 | Final Schedule Report | 8 | Electrical Engineer | 10% | 9.12 | FS | 2029-04-15 | 2029-04-22 | 2027-07-21 | 2027-07-28 | 634 | bar: 2029-04-09 to 2029-04-16
9.14 | Management Review | 2 | Subcontractor Team | 35% | 9.13 | FS | 2029-04-23 | 2029-04-24 | 2027-07-25 | 2027-07-26 | 638 | bar: 2029-04-23
9.15 | Project Closure Report | 10 | Fiber Installation Team | 80% | 9.14 | FS | 2029-04-25 | 2029-05-04 | 2027-07-26 | 2027-08-04 | 639 | bar: 2029-04-23 to 2029-04-30
9.16 | Archive Project Records | 2 | Design Engineer | 75% | 9.15 | FS | 2029-05-05 | 2029-05-06 | 2027-07-31 | 2027-08-01 | 644 | bar: 2029-04-30

## FS Summary
Finish-to-Start (FS) Schedule — Management Summary
Schedule Comparison
Project FS Start | 2026-01-05 | Metric | Days
Project FS Finish | 2029-05-06 | Baseline | 577
FS Duration | 1218 | Pure FS | 1218
Detailed Activities | 181
Total Activity Duration | 1218
Baseline Project Finish | 2027-08-04
FS Extension vs Baseline | 641
Management Interpretation
This is a pure Finish-to-Start training scenario. Every detailed activity is linked to the previous detailed activity, so no successor can start until its predecessor finishes. The resulting FS finish is intentionally compared with the original baseline to show the schedule impact of removing parallel execution.
Key CEO Question
Which activities can genuinely run in parallel? A pure FS chain is conservative and may overstate project duration. In a real EPC schedule, FS, SS, FF and lags should be used according to actual work interfaces.